## BUILDING CONTRACT PG 1 BC01
FIJI STANDARD FORM OF |  |  |  | or, in the event of his death or ceasing to be the Supervising Officer for the |  |  |  |  | APPENDIX 1 | [5 empty] | FIJI STANDARD FORM OF
|  |  |  | purpose of this Contract, such other person as the Employer shall nominate |  |  |  |  | FIJI STANDARD FORM OF BUILDING CONTRACT WITHOUT QUANTITIES
BUILDING CONTRACT |  |  |  | for that purpose, not being a person to whom the Contractor shall object for |  |  |  |  | PRIVATE EDITION 1978 | [5 empty] | BUILDING CONTRACT
|  |  |  | reasons considered to be sufficient by an arbitrator appointed in accordance | [7 empty] | CLAUSE
|  |  |  | with clause 33 of the said Conditions. Provided always that no person |  |  |  |  | Defects Liability Period ( if none other stated is 6
WITHOUT QUANTITIES PRIVATE EDITION 1978 |  |  |  | subsequently appointed to be the Supervising Officer under this Contract |  |  |  |  | months from the day named in the Certificate of |  |  | 15,16 & 30 |  |  | WITHOUT QUANTITIES PRIVATE EDITION 1978
|  |  |  | shall be entitled to disregard or overrule any certificate or opinion or |  |  |  |  | Practical Completion of the Works ). |  |  |  | 6 months
decision or approval or instruction given or expressed by the Supervising
ARTICLES OF AGREEMENT |  |  |  | Officer for the time being. |  |  |  |  | Insurance Cover for any one occurrence or series of | [5 empty] | AGREEMENT
[9 empty] | occurrences arising out of one event. |  |  | 19 (1) (a) | $3,000,000.00
4(A)
DATED | : |  | 02-09-2021 | The term 'the Quantity Surveyor' (4) in the said Conditions shall mean |  |  |  |  | Percentage to Cover Professional Fees |  |  | 20 ( A) | 10% |  | DATED |  | :
|  |  |  | COMPANY NAME |  |  |  | N/A
|  |  |  | OF |  |  |  | N/A | Date for Possession |  |  | 21 | to be advised |  | AND SCHEDULE OF CONDITIONS OF BUILDING CONTRACT
or, in the event of his death or ceasing to be the Quantity Surveyor for the
BETWEEN | : |  |  | purpose of this Contract, such other person as the Employer shall nominate |  |  |  |  | Date for Completion |  |  | 21 | to be advised |  | BETWEEN |  | :
EMPLOYER |  |  |  | for that purpose, not being a person to whom the Contractor shall object for | [10 empty] | EMPLOYER | [5 empty] | 1.3
of registered office is situated at |  |  |  | reasons considered to be sufficient by an arbitrator appointed in accordance |  |  |  |  | Liquidated & Ascertained Damages at the rate of ( VIP) |  |  | 22 | $1,000.00 / day
with clause 33 of the said Conditions.
AND | : | [7 empty] | Prime Cost Sum - items the Contractor wants to Tender |  |  | 27 (g) |  |  | AND |  | :
CONTRACTOR |  |  | JACKS MANUFACTURING PTE LTD | 4(B) | [10 empty] | CONTRACTOR | [5 empty] | JACKS MANUFACTURING PTE LTD
of registered office is situated at |  |  |  | The functions ascribed by the said Conditions of Contract to the Quantity |  |  |  |  | Period of Interim Certificates (none stated then 1 month) |  |  | 30 (1) | 1 month
Surveyor (4) shall be exercised by:
of the other part |  |  |  | COMPANY NAME |  |  |  | N/A | Retention Percentage (16)(if less than five percent - the |  |  | 30 (3) | 5.00%
WHEREAS the Employer is desirous of (1) |  |  |  | OF |  |  |  | N/A | percentage will be five percent unless a lower rate is
|  |  | test | or, in the event of his death or ceasing to exercise the functions of the |  |  |  |  | specified here). |  | At practical completion |  | 2.50%
Quantity Surveyor for the purpose of this Contract, by such other person as
THE WORKS AT |  |  | test | the Employer shall nominate for that purpose, not being a person to whom |  |  |  |  | Period of Final Measurement and Valuation ( if none
|  |  |  | the Contractor shall object for reasons considered to be sufficient by an |  |  |  |  | stated is 6 months from the day named in the |  |  | 30 (5) | 6 months
|  |  |  | Arbitrator appointed in accordance with Clause 33 of the said Conditions. |  |  |  |  | Certificate of Practical Completion of the Works)
and has caused Drawings and a Specification including Sheets XO01 ,
XO02 & XO03 showing & describing the work to be done to be prepared |  |  |  | As Witness the hands of the said parties. (5) |  |  |  |  | Minimum amount for Interim Certificates |  |  | minimum | $10,000.00
by or under the direction
OF (2) |  |  | DESIGN HUT | Signed by the said |  |  |  |  | Bank Guarantee |  |  | Appendix 2 | 10%
test2
|  |  | 26 MARA ROAD, | EMPLOYER
NAUSORI.
INDEX TO THE STANDARD FORM OF BUILDING CONTRACT
AND WHEREAS the said Drawings numbered (Refer Drawing Schedule) |  |  |  | Address
inclusive (hereinafter referred to as 'the Contract Drawings' and | [8 empty] | CLAUSE |  |  |  | SHEET
the Specification including Sheets XO01, XO02 & XO03 (hereinafter | [8 empty] | 1 | Contractor's Obligations |  |  | BC02
referred to as 'the Specification') have been signed by or on behalf of the |  |  |  | Name |  |  |  |  | 2 | Architect's Instructions |  |  | BC02
parties hereto AND WHEREAS the contractor has made an estimate | [8 empty] | 3 | Contract Documents |  |  | BC02
of the sum which he will require for carrying out the said work; |  |  |  | Description |  |  |  |  | 4 | Statutory Obligations, Notices, Fees and Charges |  |  | BC02
[9 empty] | 5 | Levels and Settings Out of the Works |  |  | BC02
NOW IT IS HEREBY AGREED AS FOLLOWS: | [8 empty] | 6 | Materials, Goods & Workmanship |  |  | BC02
1 |  |  |  | Sign |  |  |  | Common Seal | 7 | Royalties and Patent Rights |  |  | BC02
For the consideration hereinafter mentioned the Contractor will upon | [8 empty] | 8 | Foreman-In-Charge |  |  | BC02
and subject to the Conditions annexed hereto carry out and complete the |  |  |  | in the presence of WITNESS |  |  |  |  | 9 | Access for Architect to the Works |  |  | BC02
Works hown upon the Contracts Drawings and described by or referred | [8 empty] | 10 | Clerk of Works |  |  | BC02
to in the Specification and in the said Conditions. | [8 empty] | 11 | Variations, Provisional and Prime Cost Sums |  |  | BC03 |  | NOTES :
|  |  |  | Name |  |  |  |  | 12 | Quality and Quantity of the Work |  |  | BC03
2 | [8 empty] | 13 | Contract Sum |  |  | BC03 |  | 1 | State nature of intended Works.
The Employer will pay to the Contractor the sum of : | [8 empty] | 14 | Materials and Goods Unfixed or Off-Site |  |  | BC03
SUM OF | : | 0 |  | Address |  |  |  |  | 15 | Practical Completion and Defects Liability |  |  | BC03 |  | 2 | It is important that the document being used as specification should be
IN WORDS | : | [7 empty] | 16 | Partial Possession by Employer |  |  | BC03 |  |  | marked "A"
[9 empty] | 17 | Assignment or Sub-Letting |  |  | BC03
|  |  |  | Description |  |  |  | Sign | 18 | Injury to Persons & Property and Employer's Indemnity |  |  | BC03 |  | 3 | Article 3 (A) is applicable where the person concerned is entitled to the
[9 empty] | 19 | Insurance Against Injury to Person and Property |  |  | BC03 |  |  | use of the name 'Architect' under and in accordance with the Architects
(hereinafter referred to as 'the Contract Sum') or such other sum as shall | [8 empty] | 19A | Excepted Risks - Nuclear Perils etc. |  |  | BC03 |  |  | Ordiance ( Chapter 232). Article 3 (B) is applicabale in all other cases.
become payable hereunder at the times and in the manner specified in |  |  |  | As Witness the hands of the said parties. (5) |  |  |  |  | 20 | Insurance of the Works Against Fire, etc. |  |  | BC04 |  |  | Complete whichever is appropriate and delete the alternative.
the said Conditions. | [8 empty] | 21 | Possession and Completion and Postponement |  |  | BC04
|  |  |  | Signed by the said |  |  |  |  | 22 | Damages for Non-Completion |  |  | BC04 |  | 4 | Article 4(A) is to apply where a Quantity Surveyor is appointed, and Article
3(A) | [8 empty] | 23 | Extension of Time |  |  | BC04 |  |  | 4 (8) is to apply where no Quantity Surveyor is appointed. Complete
The term 'the Architect (3) in the said Conditions shall mean |  |  |  | CONTRACTOR |  |  |  |  | 24 | Loss and Expenses Caused by Disturbance of the Works |  |  | BC04 |  |  | whichever is appropriate and delete the alternative.
ARCHITECT | : |  | DESIGN HUT |  | JACKS MANUFACTURING PTE LTD |  |  |  | 25 | Determination by Employer |  |  | BC05
[9 empty] | 26 | Determination by Contractor |  |  | BC05 |  | 5 | If the contract is to be executed under seal, this clause and the words
OF | : |  | 26 MARA ROAD , NAUSORI | Address |  |  |  |  | 27 | Nominated Sub-Contractors |  |  | BC06 |  |  | following must be altered accordingly.
[9 empty] | 28 | Nominated Suppliers |  |  | BC06
or,in the event of his death or ceasing to be the Architect for the purpose | [8 empty] | 29 | Artists and Tradesmen |  |  | BC06 |  | 15 | It is suggested that the periods should be (i) three months and (ii) one
of this Contract,such other person as the Employer shall nominate for |  |  |  | Name |  |  |  |  | 30 | Certificates and Payments |  |  | BC06 |  |  | month. It is essential that periods be inserted since otherwise no period of
that purpose, not being a person to whom the Contractor shall object for |  |  |  |  | Amish Patel |  |  |  | 31A | Fluctuations |  |  | BC06 |  |  | delay would be prescribed. Refer to Extension of Time (EoT) clause.
reasons considered to be sufficient by an arbitrator appointed in |  |  |  | Description |  |  |  |  | 31B | Fluctuations |  |  | BC07
accordance with clause 33 of the said Conditions. Provided always | [8 empty] | 31C | Fluctuations |  |  | BC07 |  | 16 | The Percentage will be five per cent unless a lower rate is specified here.
that no person subsequently appointed to be the Architect under | [8 empty] | 31D | Fluctuations |  |  | BC07
this Contract shall be entitled to disregard or overrule any certificate or |  |  |  | Sign |  |  |  | Common Seal | 31E | Fluctuations |  |  | BC07
opinion or decision or approval or instruction given or expressed by | [8 empty] | 32 | Antiquities |  |  | BC07 |  | This Form is issued and Published by
the Architect for the time being. |  |  |  | in the presence of WITNESS |  |  |  |  | 33 | Arbitration |  |  | BC07 |  | The Fiji Joint Contracts Tribunal
[9 empty] | APPENDIX 1 |  | FIJI STANDARD FORM OF BUILDING CONTRACT |  | BC01 |  | PO Box 1171, 108 Amy Street, Suva, FIJI.
3(B) | [8 empty] | APPENDIX 2 |  | PERFORMANCE BOND |  | XO01 |  | The constituent bodies of the Fiji Joint Contracts Tribunal are:
The term 'the Architect' (3) in the said Conditions shall be deemed to |  |  |  | Name |  |  |  |  | APPENDIX 3 |  | GENERAL CONDITIONS OF TENDER |  | XO01 |  | Fiji Association of Architects
have been deleted throughout & replaced with the term 'the Supervising | [8 empty] | APPENDIX 4 |  | MATERIALS SUPPLIED & GENERAL CONDITIONS |  | XO02 |  | Fiji Institute of Engineers
Officer', which term shall mean |  |  |  | Address |  |  |  |  | APPENDIX 5 |  | MEMO ON GENERAL CONDITIONS OF TENDER |  | XO05 |  | Fiji Institute of Quantity Surveyors
|  |  | N/A | [5 empty] | APPENDIX 6 |  | TENDER FORM |  | XO05 |  | Fiji Master Builders Association (Inc.)
OF |  |  | N/A | Description |  |  |  | Sign | APPENDIX 7 |  | DRAWING REGISTER |  | XO05 |  | Ministry of Infrastructure & Public Utilities
Copyright reserved in all drawings and the | [5 empty] | EMPLOYER | CONTRACTOR |  |  |  | PROJECT |  |  | SHEET TITLE |  |  |  | DESIGN | : SP | PROJECT NO: | 1
work executed from them. Figured dimensions | [10 empty] | test2 |  |  | FIJI STANDARD FORM OF
shall be read in preferance. Largest scaled | [13 empty] | BUILDING CONTRACT |  |  |  | PREP BY | admin | SHEET NO. | BC01
drawings shall take precedence. Check all |  |  | ARCHITECTS,DESIGN CONSULTANTS,PROJECT MANAGERS,INTERIOR DESIGNERS 26 MARA ROAD , P.O.BOX 16 , NAUSORI , FIJI ISLANDS PH.- 3400 287 , Email : designhut@connect.com.fj |  |  | WITNESS | WITNESS
dimensions on site. All discrepancies shall | [10 empty] | test |  |  | WITHOUT QUANTITIES |  |  |  | DATE | 02-09-2021 | REV:
be reported to the ARCHITECT ASAP | [10 empty] | test |  |  | PRIVATE EDITION 1978
Note on T88: Admin:

## BC02
The Conditions hereinbefore referred to | [6 empty] | (2)
1 | Contractor's Obligations | [5 empty] | (a) | Immediately after the execution of this Contract the Architect without | [9 empty] | issued in accordance with clause 11(1) of these Conditions, & | [5 empty] | the Contractor shall supply and use in carrying out the Works any patented
(1) | [7 empty] | charge to the Contractor shall furnish him (unless he shall have been | [9 empty] | the Contractor has complied with subparagraph (ii). | [5 empty] | articles, processes or inventions, the Contractor shall not be liable in respect
The Contractor shall & upon subject to these Conditions carry out and | [7 empty] | previously furnished) with: | [8 empty] | (e) | Provided that the Contractor complies with paragraph (b) of this sub- | [5 empty] | of any infringement or alleged infringement of any patent rights in relation to
complete the works shown upon the Contract Drawings & described by or | [7 empty] | (i) | one copy certified on behalf of the Employer of the Articles of | [8 empty] | clause, the Contractor shall not be liable to the Employer under this | [5 empty] | any such articles, processes and inventions and all royalties damages or
referred to in the Specification & in the Articles of Agreement and these | [8 empty] | Agreement and of those Conditions, | [8 empty] | Contract if the Works do not comply with the statutory requirements | [5 empty] | other monies which the Contractor may be liable to pay to the persons
Conditions (which Drawings, Specification, Articles of Agreement and | [7 empty] | (ii) | two copies of the Contract Drawings, and | [8 empty] | where and to the extent that such noncompliance of the Works results | [5 empty] | entitled to such patent rights shall be added to the Contract Sum.
Conditions are hereinafter called 'the Contract Documents') in compliance | [7 empty] | (iii) | two copies of the Specification. | [8 empty] | from the Contractor having carried out work in accordance with the
therewith, using materials & workmanship of the quality & standards therein | [17 empty] | documents referred to in clause 1(2) of these Conditions or any
specified, provided that where & to the extent that approval of the quality of | [6 empty] | (b) | Immediately after the execution of this Contract the Contractor without | [9 empty] | variation instruction issued in accordance with clause 11(1) of these | [5 empty] | 8 | Foreman-In-Charge
materials or of the standards of workmanship is a matter for the opinion of | [7 empty] | charge to the Employer shall furnish the Architect (unless he shall have | [9 empty] | Conditions. | [5 empty] | The Contractor shall constantly keep upon the Works a competent foreman
the Architect, such quality and standards shall be to the reasonable | [7 empty] | been previously furnished) with a schedule of the rates upon which the | [8 empty] | (2) | The Contractor shall pay and indemnify the Employer against liability in | [5 empty] | -in-charge & any instructions given to him by the Architect shall be deemed
satisfaction of the Architect. | [7 empty] | Contractor's estimate was based. Such schedule is hereinafter referred | [9 empty] | respect of any fees or charges (including any rates or taxes) legally | [5 empty] | to have been issued to the Contractor.
(2) | [7 empty] | to as 'the Schedule of Rates'. | [9 empty] | demandable under any Act of Parliament, any instrument, rule or order
If the Contractor shall find any discrepancy in or divergence between any | [6 empty] | (3) | [10 empty] | made under any Act of Parliament, or any regulation or byelaw of any local | [5 empty] | 9 | Access for Architect to the Works
two or more of the following documents, including a divergence between | [7 empty] | As and when from time to time as may be necessary the Architect without | [9 empty] | authority or of any statutory undertaker in respect of the Works. Provided | [5 empty] | The Architect and his representatives shall at all reasonable times have
parts of anyone of them or between documents of the same description, | [7 empty] | charge to the Contractor shall furnish him with two copies of such drawings | [9 empty] | that the amount of any such fees or charges (including any rates or taxes) | [5 empty] | access to the Works and to the workshops or other places of the Contractor
namely: | [7 empty] | or details as are reasonably necessary either to explain and amplify the | [9 empty] | shall be added to the Contract Sum unless they | [5 empty] | where work is being prepared for the Contract, and when work is to be so
[8 empty] | Contract Drawings or to enable the Contractor to carry out and complete | [8 empty] | (a) | arise in respect of work executed or materials or goods supplied by a | [5 empty] | prepared in workshops or other places of a sub-contractor (whether or not a
| (i) | The Contract Drawings, | [5 empty] | these Conditions. | [9 empty] | local authority or statutory undertaker for which a prime cost sum is | [5 empty] | nominated sub-contractor as defined in clause 27 of these Conditions) the
| (ii) | The Specification, |  |  |  |  | (4) | [10 empty] | included in the Specification or for which a prime cost sum has arisen | [5 empty] | Contractor shall by a term in the sub-contract so far as possible secure a
| (iii) | any instructions issued by the Architect under these conditions | [5 empty] | The Contractor shall keep one copy of the Contract Drawings, one copy of | [9 empty] | as a result of Architect's instructions given under clause 11(3) of these | [5 empty] | similar right of access to those workshops or places for the Architect & his
|  | (save insofar as any such instruction requires a variation | [5 empty] | the Specification, and one copy of the drawings and details referred to in | [9 empty] | Conditions, or | [5 empty] | representatives and shall do all things reasonably necessary to make such
|  | in accordance with the provisions of clause | [5 empty] | sub-clause (3) of this Condition upon the Works so as to be available to the | [8 empty] | (b) | are priced or stated by way of a provisional sum in the Specification. | [5 empty] | right effective.
|  | 11(1) of these Conditions), and | [5 empty] | Architect or his representative at all reasonable times. | [8 empty] | (3) | None of the provisions of clause 27 (nominated sub-contractors) nor of
| (iv) | any drawings or documents issued by the Architect |  |  |  |  | (5) | [10 empty] | clause 28 (nominated suppliers) of these Conditions shall apply where | [5 empty] | 10 | Clerk of Works
|  | under clause 3(3),clause 3(4) or clause 5 of these shall | [5 empty] | Upon final payment under clause 30(6) of these Conditions the Contractor | [9 empty] | prime cost sums are included in the Specification or arise as a result of an | [5 empty] | The Employer shall be entitled to appoint a clerk of works whose duty shall
|  | immediately give to the Architect a written notice | [5 empty] | shall if so requested by the Architect, forthwith return to the Architect all | [9 empty] | instruction by the Architect in regard to the expenditure of provisional sums | [5 empty] | be to act solely as inspector on behalf of the Employer under the directions
|  | specifying the discrepancy or divergence, and the Architect | [5 empty] | drawings, details, specifications, descriptive schedules & other documents | [9 empty] | in respect of any fees or charges for work executed or materials or goods | [5 empty] | of the Architect, and the Contractor shall afford every reasonable facility for
|  | shall issue instructions in regard thereto. | [5 empty] | of a like nature which bear his name. | [9 empty] | supplied by a local authority or statutory undertaker solely in pursuance | [5 empty] | the performance of that duty. If any directions are given to the Contractor or
[7 empty] | (6) | [10 empty] | of its statutory obligations. Such fees or charges shall be dealt with under | [5 empty] | to his foreman upon the Works by the clerk of works the same shall be of no
2 | Architects Instructions | [6 empty] | None of the documents hereinbefore mentioned (except the Schedule of | [9 empty] | the provisions or sub-clause (2) of this Condition & any amount properly | [5 empty] | effect unless given in regard to a matter in respect of which the Architect is
(1) | [7 empty] | Rates) and no bill of quantities or other statement as to quantities of work at | [9 empty] | paid by the Contractor to any local authority or statutory undertaker shall be | [5 empty] | expressly empowered by these Conditions to issue instructions and unless
The Contractor shall (subject to sub-clauses (2) and (3) of this Condition) | [7 empty] | any time supplied to the Contractor shall be used by him for any purpose | [9 empty] | added to the amount that would otherwise be stated as due in the next | [5 empty] | confirmed in writing by the Architect within two working days of their being
forthwith comply with all instructions issued to him by the Architect in regard | [7 empty] | other than this Contract and neither the Employer, the Architect nor the | [9 empty] | interim certificate. | [5 empty] | given. If any such directions are so given and confirmed then as from the
to any matter in respect of which the Architect is expressly empowered by | [7 empty] | Quantity Surveyor shall divulge or use except for the purpose of this | [15 empty] | date of confirmation they shall be deemed to be Architect's instructions.
these Conditions to issue instructions. If within seven days after receipt of a | [7 empty] | Contract any of the rates in the Schedule of Rates. | [8 empty] | 5 | Levels and Setting Out of the Works
written notice from the Architect requiring compliance with an instruction the | [6 empty] | (7) | [9 empty] | The Architect shall determine any levels which may be required for the | [6 empty] | 11 | Variations, Provisional & Prime Cost Sums
Contractor does not comply therewith, then the Employer may employ and | [7 empty] | Any certificate to be issued by the Architect under these Conditions shall be | [8 empty] | execution of the Works, & shall furnish to the Contractor by way of | [6 empty] | (1)
pay other persons to execute any work whatsoever which may be necessary | [7 empty] | issued to the Contractor. | [8 empty] | accurately dimensioned drawings such information as shall enable the | [6 empty] | The Architect may issue instructions requiring a variation & he may sanction
to give effect to such instruction and all costs incurred in connection with | [16 empty] | Contractor to set out the Works at ground level. Unless the Architect shall | [6 empty] | in writing any variation made by the Contractor otherwise than pursuant to
such employment shall be recoverable from the Contractor by the Employer | [6 empty] | 4 |  | Statutory Obligations, Notices, Fees & Charges | [7 empty] | otherwise instruct, in which case the contract sum shall be adjusted | [6 empty] | an instruction of the Architect. No variation required by the Architect or
as a debt or may be deducted by him from any monies due or to become | [6 empty] | (1) | [9 empty] | accordingly, the Contractor shall be responsible for and shall entirely at his | [6 empty] | subsequently sanctioned by him shall vitiate this Contract.
due to the Contractor under this Contract. | [6 empty] | (a) | The Contractor shall comply with, and give all notices required by, any | [8 empty] | own cost amend any errors arising from his own inaccurate setting out. | [6 empty] | (2)
(2) | [7 empty] | Act of Parliament, any instrument rule or order made under any Act of | [15 empty] | The term 'variation' as used in these Conditions means the alteration or
Upon receipt of what purports to be an instruction issued to him by the | [7 empty] | Parliament, or any regulation or byelaw of any local authority or of any | [8 empty] | 6 | Materials, Goods and Workmanship to Conform to Description, | [5 empty] | modification of the design, quality or quantity of the Works as shown upon
Architect the Contractor may request the Architect to specify in writing the | [7 empty] | statutory undertaker which has any jurisdiction with regard to the | [9 empty] | Testing and Inspection | [5 empty] | the Contract Drawings and described by or referred to in the Specification,
provision of these Conditions which empowers the issue of the said | [7 empty] | Works or with whose systems the same are or will be connected | [8 empty] | (1) | [6 empty] | & includes the addition, omission or substitution of any work, the alteration
instruction. The Architect shall forthwith comply with any such request, and | [7 empty] | (all requirements to be so complied with being referred to in these | [8 empty] | All materials, goods and workmanship shall so far as procurable be of the | [6 empty] | of the kind or standard of any of the materials or goods to be used in the
if the Contractor shall there after comply with the said instruction (neither | [7 empty] | Conditions as 'the statutory requirements'). | [8 empty] | respective kinds and standards described in the Specification. | [6 empty] | Works, and the removal from the site of any work materials or goods
party before such compliance having given to the other a written request to | [6 empty] | (b) | If the Contractor shall find any divergence between the statutory | [8 empty] | (2) | [6 empty] | executed or brought thereon by the Contractor for the purposes of the
concur in the appointment of an arbitrator under clause 33 of these | [7 empty] | requirements & all or any of the documents referred to in clause 1 (2) | [8 empty] | The Contractor shall upon the request of the Architect furnish him with | [6 empty] | Works other than work materials or goods which are not in accordance with
Conditions in order that it may be decided whether the provision specified | [7 empty] | of these Conditions or any variation instruction issued in accordance | [8 empty] | vouchers to prove that the materials and goods comply with sub-clause (1) | [6 empty] | this Contract.
by the Architect empowers the issue of the said instruction), then the issue | [7 empty] | with clause 11(1) of these Conditions, he shall immediately give to the | [8 empty] | of this Condition. | [6 empty] | (3)
of the same shall be deemed for all the purposes of this Contract to have | [7 empty] | Architect a written notice specifying the divergence. | [8 empty] | (3) | [6 empty] | The Architect shall issue instructions in regard to the expenditure of prime
been empowered by the provision of these Conditions specified by the | [6 empty] | (c) | If the Contractor gives notice under paragraph (b) of this sub-clause or | [8 empty] | The Architect may issue instructions requiring the Contractor to open up for | [6 empty] | cost (6) and provisional sums included in the Specification and of prime cost
Architect in answer to the Contractor's request. | [7 empty] | if the Architect shall otherwise discover or receive notice of a | [8 empty] | inspection any work covered up or to arrange for or carry out any test of any | [6 empty] | sums which arise as a result of instructions issued in regard to the
(3) | [7 empty] | divergence between the statutory requirements and all or any of the | [8 empty] | materials or goods (whether or not already incorporated in the Works) or of | [6 empty] | expenditure of provisional sums.
All instructions issued by the Architect shall be is ued in writing. Any | [7 empty] | documents referred to in clause 1(2) of these Conditions or any | [8 empty] | any executed work, & the cost of such opening up or testing (together with | [6 empty] | (4)
instruction issued orally shall be of no immediate effect, but shall be | [7 empty] | variation instruction issued in accordance with clause 11(1) of these | [8 empty] | the cost of making good in consequence thereof) shall be added to the | [6 empty] | All variations required by the Architect or subsequently sanctioned by him in
confirmed in writing by the Contractor to the Architect within seven days, & | [7 empty] | Conditions, the Architect shall within 7 days of the discovery or receipt | [8 empty] | Contract Sum unless provided for in the Specification or unless the | [6 empty] | writing & all work executed by the Contractor for which provisional sums are
if not dissented from in writing by the Architect to the Contractor within | [7 empty] | of a notice issue instructions in relation to the divergence. If and insofar | [8 empty] | inspection or test shows that the work, materials or goods are not in | [6 empty] | included in the Specification (other than work for which a tender made under
seven days from receipt of the Contractor's confirmation shall take effect as | [7 empty] | as the instructions require the Works to be varied, they shall be | [8 empty] | accordance with this Contract. | [6 empty] | clause 27 (g) of these Conditions has been accepted) shall be measured &
from the expiration of the latter said seven days. Provided always: | [7 empty] | deemed to be Architect's instructions issued in accordance with clause | [8 empty] | (4) | [6 empty] | valued by the Quantity Surveyor who shall give to the Contractor an
[8 empty] | of the Conditions. | [8 empty] | The Architect may issue instructions in regard to the removal from the site | [6 empty] | opportunity of being present at the time of such measurement and of taking
(a) | That if the Architect within seven days of giving such an oral instruction | [5 empty] | (d) | (i) | If in any emergency compliance with paragraph (a) of this sub- | [7 empty] | of any work, materials or goods which are not in accordance with this | [6 empty] | such notes & measurements as the Contractor may require. The valuation
| shall himself confirm the same in writing, then the Contractor shall not | [7 empty] | clause requires the Contractor to supply materials or execute | [7 empty] | Contract. | [6 empty] | of variations and of work executed by the Contractor for which a provisional
| be obliged to confirm as aforesaid, and the said instruction shall take | [7 empty] | work before receiving instructions under paragraph (c) of this | [7 empty] | (5) | [6 empty] | sum is included in the Specification (other than work for which a tender has
| effect as from the date of the Architect's confirmation, and | [7 empty] | sub-clause the Contractor shall supply such limited materials & | [7 empty] | The Architect may (but not unreasonably or vexatiously) issue instructions | [6 empty] | been accepted as aforesaid) unless otherwise agreed shall be made in
(b) | That if neither the Contractor nor the Architect shall confirm such an | [7 empty] | execute such limited work as are reasonably necessary to | [7 empty] | requiring the dismissal from the Works of any person employed thereon. | [6 empty] | accordance with the following rules:
| oral instruction in the manner and at the time aforesaid but the | [7 empty] | secure immediate compliance with the statutory requirements. | [14 empty] | (a) | The prices in the Schedule of Rates shall determine the valuation of
| Contractor shall nevertheless comply with the same, then the Architect | [6 empty] | (ii) | The Contractor shall forthwith inform the Architect of the | [7 empty] | 7 | Royalties and Patent Rights | [6 empty] | work of similar character executed under similar conditions as work
| may confirm the same in writing at any time prior to the issue of the | [7 empty] | emergency & of the steps that he is taking under this paragraph | [7 empty] | All royalties or other sums payable in respect of the supply & use in carrying | [7 empty] | priced therein;
| Final Certificate, and the said instruction shall thereupon be deemed to | [7 empty] | of this Condition. | [7 empty] | out the Works as described by or referred to in the Specification of any | [6 empty] | (b) | The said prices, where work is not of a similar character or executed
| have taken effect on the date on which it was issued. | [6 empty] | (iii) | Work executed and materials supplied by the Contractor under | [7 empty] | patented articles, processes or inventions shall be deemed to have been | [7 empty] | under similar conditions as aforesaid, shall be the basis of prices for
[9 empty] | sub-paragraph (i) of this paragraph shall be deemed to have | [7 empty] | included in the Contract Sum, and the Contractor shall indemnify the | [7 empty] | the same so far as may be reasonable, failing which a fair valuation
3 | Contract Documents | [7 empty] | been executed & supplied pursuant to an Architect's instruction | [7 empty] | Employer from and against all claims, proceedings, damages, costs and | [7 empty] | thereof shall be made;
(1) | [8 empty] | in accordance with clause 11(1) of these Conditions provided | [7 empty] | expenses which may be brought or made against the Employer or to which
The Contract Drawings, the Specification and the Schedule of Rates | [8 empty] | that the emergency arose because of a divergence between the | [7 empty] | he may be put by reason of the Contractor infringing or being held to have | [6 empty] | (6) The term 'prime cost' may be indicated by the abbreviation 'P.C.' in any
hereinafter referred to shall remain in the custody of the Architect so as to | [8 empty] | statutory requirements & all or any of the documents referred to | [7 empty] | infringed any patent rights in relation to any such articles, processes and | [6 empty] | document relating to this Contract (including the Specification), & wherever
be available at all reasonable times for the inspection of the Employer or of | [8 empty] | in clause 1(2) of these Conditions or any variation instruction | [7 empty] | inventions. Provided that where in compliance with Architect's instructions | [6 empty] | the abbreviation is used it shall be deemed to mean 'prime cost'.
Copyright reserved in all drawings and the | [8 empty] | EMPLOYER |  | CONTRACTOR | [6 empty] | PROJECT |  |  | SHEET TITLE | [5 empty] | DESIGN | : SP | PROJECT NO. | 1
work executed from them. Figured dimensions | [17 empty] | test2 |  |  | FIJI STANDARD FORM OF
shall be read in preferance. Largest scaled | [20 empty] | BUILDING CONTRACT | [5 empty] | PREP BY | admin | SHEET NO. | BC02
drawings shall take precedence. Check all |  |  | ARCHITECTS,DESIGN CONSULTANTS,PROJECT MANAGERS,INTERIOR DESIGNERS 26 MARA ROAD , P.O.BOX 16 , NAUSORI , FIJI ISLANDS PH.- 3400 287 , Email : designhut@connect.com.fj | [5 empty] | WITNESS |  | WITNESS
dimensions on site. All discrepancies shall | [17 empty] | test |  |  | WITHOUT QUANTITIES | [5 empty] | DATE | 02-09-2021 | REV:
be reported to the ARCHITECT ASAP | [17 empty] | test |  |  | PRIVATE EDITION 1978
less 0.29
7 | 7 | 61.85 | 64.57 | 5 | 9.55 |  | 7 | 7 | 9.11 | 59.6 | 21.57 | 26.57 | 5 | 8.43 | 9 |  | 7 | 7 | 90 | 32.43 | 5 | 14.34 |  | 8 | 7 | 38.96 | 22 | 22 | 35 | 22
13.38
12 | 12 | 51.85 | 64.57 | 5 | 9.55 | 5 |  | 14.89 | 9.11 | 59.6 | 21.57 | 26.57 | 5 | 8.43 | 9.8 | 5 | 6.2 | 5.8 | 79.2 | 32.43 | 5 | 14.34 | 5 | 12 | 12 | 29.96 | 22 | 22 | 35 | 22 | 154.96 | 168.34
43.34
28.71 | 7.43 | 39.71 | 64.57 | 5 | 8.43 |  |  | 21 | 21.57 | 47.14 | 21.57 | 26.57 | 5 | 8.43 |  |  | 21 | 2.71 | 23.29 | 32.43 | 5 | 12.43 | 15.29 | 3.29 |  | 42.29 | 22 | 22 | 35 | 22 | 563.86
548.86
[22 empty] | 1.91 | [8 empty] | 137.215

## BC03
(c) | Where work cannot properly be measured and valued the Contractor |  |  | 14 | Material & Goods Unfixed or Off-Site |  |  | (c) | When in the opinion of the Architect any defects, shrinkages or other |  |  |  | sub-contractor in respect of personal injury or death arising out of or in
| shall unless otherwise agreed be allowed: |  |  | (1) |  |  |  |  | faults in the relevant part which he may have required to be made |  |  |  | the course of or caused by the carrying out of the Works not due to any
| (i) | the prime cost of such work calculated in accordance with the |  | Unfixed materials & goods delivered to, placed on or adjacent to the Works |  |  |  |  | good under sub-clause (2) or subclause (3) of clause 15 of these |  |  |  | act or neglect of the Employer or of any person for whom the Employer
|  | 'Definition of Prime Cost of Daywork carried out under a |  | and intended therefore shall not be removed except for use upon the Works |  |  |  |  | Conditions shall have been made good he shall issue a certificate to |  |  |  | is responsible and in respect of injury or damage to property, real or
|  | Building Contract' issued by the Fiji Association of Architects & |  | unless the Architect has consented in writing to such removal which consent |  |  |  |  | that effect. |  |  |  | personal, arising out of or in the course of or by reason of the carrying
|  | the Fiji Master Builders' Association and current at the date of |  | shall not be unreasonably withheld. Where the value of any such materials |  |  |  | (d) | The Contractor shall reduce the value insured under clause 20(A) of |  |  |  | out of the Works and caused by any negligence, omission or default of
|  | tender as defined in clause 31D(6)(a) of these Conditions |  | or goods has in accordance with clause 30(2) of these Conditions been |  |  |  |  | these Conditions (if applicable) by the full value of the relevant part, & |  |  |  | the Contractor, his servants or agents or, as the case may be, of such
|  | together with percentage additions to each section of the prime |  | included in any Interim Certificate under which the Contractor has received |  |  |  |  | the said relevant part shall as from the date on which the Employer |  |  |  | subcontractor, his servants or agents. The insurance in respect of
|  | cost at the rates set out by the Contractor in the Schedule of |  | payment, such materials and goods shall become the property of the |  |  |  |  | shall have taken possession thereof be at the sole risk of the Employer |  |  |  | claims for personal injury to, or the death of, any person under a
|  | Rates; or |  | Employer, but subject to clause 20(B) or clause 20(C) of these Conditions |  |  |  |  | as regards any of the contingencies referred to in the said clause. |  |  |  | contract of service or apprenticeship with the Contractor or the sub-
| (ii) | where the work is within the province of any specialist trade & |  | (if applicable), the Contractor shall remain responsible for loss or damage to |  |  |  | (e) | In lieu of any sum to be paid or allowed by the Contractor under clause |  |  |  | contractor as the case may be, and arising out of and in the course
|  | the Fiji Association of Architects, or other appropriate |  | the same. |  |  |  |  | 22 of these Conditions in respect of any period during which the Works |  |  |  | of such person's employment, shall comply with the Workmen's
|  | professional body, and the appropriate body representing the |  | (2) |  |  |  |  | may remain incomplete occurring after the date on which the Employer |  |  |  | Compensation Ordinance (Chapter 77). For all other claims to which
|  | employers in that trade have agreed and issued a definition of |  | Where the value of any materials or goods has in accordance with clause |  |  |  |  | shall have taken possession of the relevant part there shall be paid or |  |  |  | this sub-clause applies the insurance cover shall be the sum stated in
|  | prime cost of Daywork, the prime cost of such work calculated |  | 30(2A) of these Conditions been included in any Interim Certificate under |  |  |  |  | allowed such sum as bears the same ratio to the sum which would be |  |  |  | the Appendix to these Conditions (or such greater sum as the
|  | in accordance with that definition and current at the date of |  | which the Contractor has received payment, such materials and goods shall |  |  |  |  | paid or allowed apart from the provisions of this Condition as does the |  |  |  | Contractor may choose) for anyone occurrence or series of
|  | tender as defined in clause 31D(6)(a) of these Conditions |  | become the property of the Employer, & thereafter the Contractor shall not, |  |  |  |  | Contract Sum less the total value of the said relevant part to the |  |  |  | occurrences arising out of one event.
|  | together with percentage additions on the prime cost at the |  | except for use upon the Works, remove or cause or permit the same to be |  |  |  |  | Contract Sum. |  |  | (b) | As and when he is reasonably required so to do by the Architect the
|  | rates set out by the Contractor in the Schedule of Rates. |  | moved or removed from the premises where they are, but the Contractor |  |  |  | (f) |  |  |  |  | Contractor shall produce & shall cause any sub-contractor to produce
|  |  |  | shall nevertheless be responsible for any loss thereof or damage thereto & | [8 empty] | for inspection by the Employer documentary evidence that the
Provided that in any case vouchers specifying the time daily spent |  |  |  | for the cost of storage, handling and insurance of the same until such time |  |  |  |  | (i) | Within fourteen days of the date on which the Employer shall |  |  | insurances required by this sub-clause are properly maintained, but on
upon the work (and if required by the Architect the workmen's names) |  |  |  | as they are delivered to and placed on or adjacent to the Works whereupon | [5 empty] | have taken possession of the relevant part there shall be paid |  |  | any occasion the Employer may (but not unreasonably or vexatiously)
and the materials employed shall be delivered for verification to the |  |  |  | the provisions of sub-clause (1) of this clause (except the words 'where the | [5 empty] | to the Contractor from the sums then retained under clause |  |  | require to have produced for his inspection the policy or policies and
Architect or his authorised representative not later than the end of the |  |  |  | value' to the words 'the Employer but') shall apply thereto. | [5 empty] | 30(3) of these Conditions a percentage (which percentage shall |  |  | receipts in question.
week following that in which the work has been executed; | [9 empty] | be equal to half the Retention Percentage) of the total value |  | (c) | Should the Contractor or any sub-contractor make default in insuring
|  |  |  | 15 | Practical Completion & Defects Liability |  |  |  |  | (subject to paragraph (iii) of this sub-clause) of the relevant part. |  |  | or in continuing or in causing to insure as provided in this sub-clause
(d) | The prices in the Schedule of Rates shall determine the valuation of |  |  | (1) |  |  |  |  | (ii) | On the expiration of the Defects Liability Period named in the |  |  | the Employer may himself insure against any risk with respect to which
| items omitted; provided that if omissions substantially vary the |  |  | When in the opinion of the Architect the Works are practically completed, | [5 empty] | Appendix to these Conditions in respect of the relevant part or |  |  | the default shall have occurred & may deduct a sum or sums
| conditions under which any remaining items of work are carried out the |  |  | he shall forthwith issue a certificate to that effect and Practical Completion | [5 empty] | on the issue of the Certificate of Completion of Making Good |  |  | equivalent to the amount paid or payable in respect or premiums from
| prices for such remaining items shall be valued under rule (b) of this |  |  | of the Works shall be deemed for all the purposes of this Contract to have | [5 empty] | Defects in respect of the relevant part, whichever is the later, |  |  | any monies due or to become due to the Contractor.
| sub-clause. |  |  | taken place on the day named in such certificate. | [5 empty] | there shall be paid to the Contractor from the sums then |  | (2)
|  |  |  | (2) | [5 empty] | retained under clause 3 (3) of these Conditions a percentage |  | (a) | The Contractor shall maintain in the joint names of the Employer & the
(5) |  |  |  | Any defects, shrinkages or other faults which shall appear within the Defects | [5 empty] | (which percentage shall be equal to half the Retention |  |  | Contractor insurances for such amounts of indemnity as may be
Effect shall be given to the measurement and valuations of variations under |  |  |  | Liability Period stated in the appendix to these Conditions and which are the | [5 empty] | Percentage) of the total value (subject to paragraph (iii) of this |  |  | specified by way of provisional sum items in the Specification in
sub-clause (4) of this Condition in Interim Certificates and by adjustment of |  |  |  | due to materials or workmanship not in accordance with this Contract, shall | [5 empty] | sub-clause) of the relevant part. |  |  | respect of any expense, liability, loss, claim, or proceedings which the
the Contract Sum; and effect shall be given to the measurement & valuation |  |  |  | be specified by the Architect in a Schedule of Defects which he shall deliver |  |  |  |  | (iii) | Where the total value of the relevant part includes works in |  |  | Employer may incur or sustain by reason of damage to any property
of work for which a provisional sum is included in the Specification under the |  |  |  | to the Contractor not later than 14 days after the expiration of the said | [5 empty] | respect of which a final payment to a nominated sub-contractor |  |  | other than the Works caused by collapse, subsidence, vibration,
said sub-clause in Interim Certificates & by adjustment of the Contract Sum |  |  |  | Defects Liability Period, and within a reasonable time after receipt of such | [5 empty] | has been made under the provisions of clause 27(e) of these |  |  | weakening or removal of support or lowering of ground water arising
in accordance with clause 30(5)(c) of these Conditions. |  |  |  | Schedule, the Defects, shrinkages and other faults therein specified shall be | [5 empty] | Conditions, the said total value for the purposes of paragraphs |  |  | out of or in the course of or by reason of the carrying out of the Works
|  |  |  | made good by the Contractor and (unless the Architect shall otherwise | [5 empty] | (i) and (ii) of this sub-clause shall be deemed to be reduced by |  |  | excepting damage
(6) |  |  |  | instruct, in which case the Contract Sum shall be adjusted accordingly) | [5 empty] | the value of the said sub-contractor's work carried out in the |  |  | (i) | caused by the negligence, omission or default of the Contractor,
If upon written application being made to him by the Contractor, the |  |  |  | entirely at his own cost. | [5 empty] | relevant part. |  |  |  | his servants or agents or of any sub-contractor his servants or
Architect is of the opinion that a variation or the execution by the Contractor |  |  |  | (3) | [9 empty] | agents;
of work for which a provisional sum is included in the Specification (other |  |  |  | Notwithstanding sub-clause (2) of this Condition the Architect may whenever |  |  |  | 17 | Assignment or Sub Letting |  |  |  | (ii) | attributable to errors or omissions in the designing of the Works;
than work for which a tender made under clause 27(g) of these Conditions |  |  |  | he considers it necessary so to do, issue instructions requiring any defect, | [8 empty] | (iii) | attributable to errors or omissions in the designing of the Works;
has been accepted) has involved the Contractor in direct loss &/or expense |  |  |  | shrinkage or other fault which shall appear within the Defects Liability Period |  |  |  | (1) |  |  |  |  | (iv) | which is at the risk of the Employer under clause 20(B) or
for which he would not be reimbursed by payment in respect of a valuation |  |  |  | named in the appendix to these Conditions and which is due to materials or |  |  |  | The Employer shall not without the written consent of the Contractor assign | [5 empty] | clause 20(C) of these Conditions (if applicable);
made in accordance with the rules contained in sub-clause (4) of this |  |  |  | workmanship not in accordance with this Contract to be made good, and the |  |  |  | this Contract. |  |  |  |  | (v) | arising from a nuclear risk or war risk;
Condition and if the said application is made within a reasonable time of the |  |  |  | Contractor shall within a reasonable time after receipt of such instructions |  |  |  | (2)
loss or expense having been incurred, then the Architect shall either himself |  |  |  | comply with the same and (unless the Architect shall otherwise instruct, in |  |  |  | The Contractor shall not without the written consent of the Employer assign |  |  |  | (b) | Any such insurance as is referred to in the immediately preceding
ascertain or shall instruct the Quantity Surveyor to ascertain the amount of |  |  |  | which case the Contract Sum shall be adjusted accordingly) entirely at his |  |  |  | this Contract, & shall not without the written consent of the Architect (which |  |  |  |  | paragraph shall be placed with insurers to be approved by the Architect,
such loss or expense. Any amount from time to time so ascertained shall be |  |  |  | own cost. Provided that no such instructions shall be issued after delivery of |  |  |  | consent shall not be unreasonably withheld to the prejudice of the |  |  |  |  | and the Contractor shall deposit with him the policy or policies and the
added to the Contract Sum, and if an Interim Certificate is issued after the |  |  |  | a Schedule of Defects or after 14 days from the expiration of the said |  |  |  | Contractor) sub-let any portion of the Works. Provided that it shall be a |  |  |  |  | receipts in respect of premiums paid.
date of ascertainment any such amount shall be added to the amount which |  |  |  | Defects Liability Period. |  |  |  | condition in any sub-letting which may occur that the employment of the sub |  |  |  | (c) | Should the Contractor make default in insuring or in continuing to
would otherwise be stated as due in such Certificate. |  |  |  | (4) |  |  |  | -contractor under the sub-contract shall determine immediately upon the |  |  |  |  | insure as provided in this sub-clause the Employer may himself insure
|  |  |  | When in the opinion of the Architect any defects, shrinkages or other faults |  |  |  | determination (for any reason) of the Contractor's employment under this |  |  |  |  | against any risk with respect to which the default shall have occurred
12 | Quality & Quantity of the Work |  |  | which he may have required to be made good under sub-clauses (2) & (3) |  |  |  | Contract. |  |  |  |  | & the amounts paid or payable by the Employer in respect of premiums
|  |  |  | of this Condition shall have been made good he shall issue a certificate to |  |  |  | 18 | Injury to Persons & Property and Employer's |  |  |  | shall not be set against the relevant provisional sum in the settlement
(1) |  |  |  | that effect, and completion of making good defects shall be deemed for all |  |  |  |  | Indemnity |  |  |  | of accounts under clause 30(5)(c) of these Conditions.
The quality and quantity of the work included in the Contract Sum shall be |  |  |  | the purposes of this Contract to have taken place on the day named in such |  |  |  | (1)
deemed to be that which is shown upon the Contract Drawings or described |  |  |  | certificate. |  |  |  | The Contractor shall be liable for, and shall indemnify the Employer against |  |  |  | 19 | A Excepted Risks - Nuclear Perils etc.
in the Specification, but save asaforesaid nothing contained in the Contract | [7 empty] | any expense, liability, loss, claim or proceedings whatsoever arising under |  |  |  | Notwithstanding the provisions of clauses 18(2) or 19 or these Conditions,
Drawings or the Specification shall override, modify, or affect in anyway |  |  |  | 16 | Partial Possession by Employer |  |  | any statute or at common law in respect of personal injury to or the death of |  |  |  | the Contractor shall not be liable either to indemnify the Employer or to
whatsoever the application or interpretation of that which is contained in |  |  |  | If at any time or times before Practical Completion of the Works the |  |  |  | any person whomsoever arising out of or in the course of or caused by the |  |  |  | insure against any damage, loss or injury caused to the Works, the site, or
these Conditions. |  |  |  | Employer with the consent of the Contractor shall take possession of any |  |  |  | carrying out of the Works, unless due to any act or neglect of the Employer |  |  |  | any property, by the effect of ionising radiations or contamination by
(2) |  |  |  | part or parts of the same (any such part being hereinafter in this clause |  |  |  | or of any person for whom the Employer is responsible. |  |  |  | radioactivity from any nuclear fuel or from any nuclear waste from the
Any error in description or in quantity in or omission of items from the |  |  |  | referred to as 'the relevant part'), then notwithstanding anything expressed |  |  |  | (2) |  |  |  | combustion of nuclear fuel, radioactive toxic explosive or other hazardous
Contract Drawings and/or the Specification shall not vitiate this Contract but |  |  |  | or implied elsewhere in this Contract: |  |  |  | Except for such loss or damage as is at the risk of the Employer under |  |  |  | properties of any explosive nuclear assembly or nuclear component thereof,
shall be corrected and deemed to be a variation required by the Architect. | [7 empty] | clause 20(B) or clause 20(C) of these Conditions (if applicable) the |  |  |  | pressure waves caused by aircraft or other aerial devices travelling at sonic
(3) |  |  |  | (a) | Within seven days from the date on which the Employer shall have |  |  | Contractor shall be liable for, and shall indemnify the Employer against, any |  |  |  | or supersonic speeds.
Any bills of quantities or other statements as to quantities of work which |  |  |  |  | taken possession of the relevant part of the Architect shall issue a |  |  | expense, liability, loss, claim or proceedings in respect of any injury or
may at any time be supplied to the Contractor shall not form part of this |  |  |  |  | certificate stating his estimate of the approximate total value of the |  |  | damage whatsoever to any property real or personal in so far as such injury |  |  |  | 20 | [A] Insurance of the Works Against Fire etc. (7)
Contract, and the rates contained in the Schedule of Rates shall apply |  |  |  |  | said part, and for all the purposes of this Condition (but for no other) |  |  | or damage arises out of or in the course of or by reason of the carrying out |  |  |  | (1)
notwithstanding any discrepancy between such rates & anything contained |  |  |  |  | the value so stated shall be deemed to be the total value of the said |  |  | of the Works, and provided always that the same is due to any negligence |  |  |  | The Contractor shall in the joint names of the Employer and Contractor
in any such bill or other statement. |  |  |  |  | part. |  |  | omission or default of the Contractor, his servants or agents. |  |  |  | insure against loss and damage by fire, lightning, explosion, storm, tempest,
flood, bursting or overflowing of water tanks, apparatus or pipes; earthquake,
13 | Contract Sum |  |  | (b) | For the purposes of sub-paragraph (ii) of the paragraph (f) of this |  |  | 19 | Insurance Against Injury to Persons and Property |  |  | aircraft and other aerial devices or articles dropped therefrom, riot and civil
The Contract Sum shall not be adjusted or altered in any way whatsoever |  |  |  |  | Condition and subclauses (2) and (3) of clause 15 of these Conditions, |  |  | (1) |  |  |  | commotion (excluding any loss or damage caused by ionising radiations or
otherwise than in accordance with the express provision of these Conditions, |  |  |  |  | Practical Completion of the relevant part shall be deemed to have |  |  | (a) | Without prejudice to his liability to indemnify the Employer under |  |  | contamination by radioactivity from any nuclear fuel or from any nuclear
and subject to clause 12(2) of these Conditions any error whether of |  |  |  |  | occurred and the Defects Liability Period in respect of the relevant part |  |  |  | clause 18 of these Conditions the Contractor shall maintain and shall |  |  | waste from the combustion of nuclear fuel, radioactive toxic explosive or
arithmetic or not in the computation of the Contract Sum shall be deemed to |  |  |  |  | shall be deemed to have commenced on the date on which the |  |  |  | cause any subcontractor to maintain such insurances as are necessary |  |  | other hazardous properties of any explosive nuclear assembly or nuclear
have been accepted by the parties hereto. |  |  |  |  | Employer shall have taken possession thereof. |  |  |  | to cover the liability of the Contractor or, as the case may be, of such |  |  | component thereof, pressure waves caused by aircraft or other aerial
Copyright reserved in all drawings and the | [5 empty] | EMPLOYER | CONTRACTOR |  | PROJECT |  | SHEET TITLE |  |  |  | DESIGN | : SP | PROJECT NO. | 1
work executed from them. Figured dimensions | [8 empty] | test2 |  | FIJI STANDARD FORM OF
shall be read in preferance. Largest scaled | [10 empty] | BUILDING CONTRACT |  |  |  | PREP BY | admin | SHEET NO. | BC03
drawings shall take precedence. Check all |  |  | ARCHITECTS,DESIGN CONSULTANTS,PROJECT MANAGERS,INTERIOR DESIGNERS 26 MARA ROAD , P.O.BOX 16 , NAUSORI , FIJI ISLANDS PH.- 3400 287 , Email : designhut@connect.com.fj |  |  | WITNESS | WITNESS
dimensions on site. All discrepancies shall | [8 empty] | test |  | WITHOUT QUANTITIES |  |  |  | DATE | 02-09-2021 | REV:
be reported to the ARCHITECT ASAP | [8 empty] | test |  | PRIVATE EDITION 1978

## BC04
devices travelling at sonic or supersonic speeds) for the full value thereof |  |  |  |  | goods and the removal and disposal of debris shall be deemed to be |  |  |  | (ii) | the Architect may issue instructions requiring the Contractor to |  | (l) | by a local authority or statutory undertaker in carrying out work in
(plus the percentage (if any) named in the Appendix to these Conditions to |  |  |  |  | a variation required by the Architect. |  |  |  |  | remove and dispose of any debris; and |  |  | pursuance of its statutory obligations in relation to the Works, or in
cover professional fees) all work executed and all unfixed materials and |  |  |  | 2O[C] |  | (9) |  |  | (iii) | the reinstatement and making good of such loss or damage & |  |  | failing to carry out such work,
goods, delivered to, placed on or adjacent to the Works and intended |  |  |  | The existing structures together with the contents thereof owned by him or | [5 empty] | (when required) the removal and disposal of debris shall be |  | then the Architect shall so soon as he is able to estimate the length of the
therefore but excluding temporary buildings, plant, tools and equipment |  |  |  | for which he is responsible and the Works and all unfixed materials and | [5 empty] | deemed to be a variation required by the Architect. |  | delay beyond the date or time aforesaid make in writing a fair & reasonable
owned or hired by the Contractor or any sub-contractor, and shall keep such |  |  |  | goods, delivered to, placed on or adjacent to the Works and intended | [7 empty] | extension of time for completion of the Works. Provided always that the
work, materials & goods so insured until Practical Completion of the Works. |  |  |  | therefore (except temporary buildings, plant, tools and equipment owned |  |  |  | 21 | Possession, Completion & Postponement |  |  | Contractor shall use constantly his best endeavours to prevent delay and
Such insurance shall be with insurers approved by the Architect and the |  |  |  | or hired by the Contractor or any sub-contractor) shall be at the sole risk |  |  |  | (1) |  |  |  | shall do all that may reasonably be required to the satisfaction of the
Contractor shall deposit with him the policy or policies and the receipts in |  |  |  | of the 8Employer as regards loss or damage by fire, lightning, explosion, |  |  |  | On the Date for Possession stated in the Appendix to these Conditions |  |  |  | Architect to proceed with the Works.
respect of premiums paid & should the Contractor make default in insuring |  |  |  | storm, tempest, flood, bursting or overflowing of water tanks, apparatus |  |  |  | possession of the site shall be given to the Contractor who shall thereupon
or continuing to insure as aforesaid the Employer may himself insure |  |  |  | or pipes, earthquake, aircraft and other aerial devices or articles dropped |  |  |  | begin the Works and regularly and diligently proceed with the same, & who |  |  |  | 24 | Loss & Expense Caused by Disturbance of Regular
against any risk in respect of which the default shall have occurred & deduct |  |  |  | therefrom, riot and civil commotion (excluding any loss or damage |  |  |  | shall complete the same on or before the Date for Completion stated in the |  |  |  | Progress of the Works
a sum equivalent to the amount paid him in respect of premiums from any |  |  |  | caused by ionising radiations or contamination by radioactivity from any |  |  |  | said Appendix subject nevertheless to the provisions for extension of time |  |  |  | (1)
monies due or to become due to the Contractor. (8) |  |  |  | nuclear fuel or from any nuclear waste from the combustion of nuclear |  |  |  | contained in clause 23 of these Conditions. |  |  |  | If upon written application being made to him by the Contractor the Architect
|  |  |  | fuel, radioactive toxic explosive or other hazardous properties of any |  |  |  | (2) |  |  |  | is of the opinion that the Contractor has been involved in direct loss and/or
Provided always that if the Contractor shall independently of his obligations |  |  |  | explosive nuclear assembly or nuclear component thereof, pressure |  |  |  | The Architect may issue instructions in regard to the postponement of any |  |  |  | expense for which he would not be reimbursed by a payment made under
under this Contract maintain a policy of insurance which covers inter alia the |  |  |  | waves caused by aircraft or other aerial devices travelling at sonic or |  |  |  | work to be executed under the provisions of this Contract. |  |  |  | any other provision in this Contract by reason of the regular progress of the
said work, materials & goods against the aforesaid contingencies to the full |  |  |  | supersonic speeds) and the Employer shall maintain adequate insurance | [7 empty] | Works or of any part thereof having been materially affected by:
value thereof (plus the aforesaid percentage (if any)), then the maintenance |  |  |  | against those risks. If the Employer shall at any time fail upon request to | [7 empty] | (a) | The Contractor not having received in due time necessary instructions,
by the Contractor of such policy shall, if the Employer's interest in that policy |  |  |  | produce any receipt showing such a policy as aforesaid to be effective, then |  |  |  | 22 | Damages for Non-Completion |  |  |  | drawings, details or levels from the Architect for which he specifically
of insurance is endorsed thereon, be a discharge of the Contractor's |  |  |  | the Contractor may in the name and on behalf of the Employer insure the |  |  |  | If the Contractor fails to complete the Works by the Date for Completion |  |  |  |  | applied in writing on a date which having regard to the Date for
obligation to insure in the joint names of the Employer and Contractor; if & |  |  |  | existing structures together with the aforesaid contents, the Works and all |  |  |  | stated in the Appendix to these Conditions or within any extended time fixed |  |  |  |  | Completion stated in the Appendix to these Conditions or to any
so long as the Contractor is able to produce for inspection as and when he |  |  |  | unfixed materials & goods as aforesaid against loss or damage occasioned |  |  |  | under clause 23 of these Conditions & the Architect certifies in writing that in |  |  |  |  | extension of time then fixed under clause 23 of these Conditions was
is reasonably required so to do by the Architect documentary evidence that |  |  |  | by the said contingencies, & for that purpose shall have such right of entry |  |  |  | his opinion the same ought reasonably so to have been completed, then the |  |  |  |  | neither unreasonably distant from nor unreasonably close to the date
the said policy is properly endorsed & maintained then the Contractor shall |  |  |  | and inspection as may be required to make a survey and inventory of the |  |  |  | Contractor shall payor allow to the Employer a sum calculated at the rate |  |  |  |  | on which it was necessary for him to receive the same; or
be discharged from his obligation to deposit a policy or policies and receipts |  |  |  | existing structures and the aforesaid contents and shall upon production of |  |  |  | stated in the said Appendix as Liquidated and Ascertained Damages for the |  |  |  | (b) | The opening up for inspection of any work covered up or the testing of
with the Employer but on any occasion the Employer may (but not |  |  |  | the receipt for any premium paid by him be entitled to have its amount |  |  |  | period during which the Works shall so remain or have remained incomplete |  |  |  |  | any of the work materials or goods in accordance with clause 6(3) of
unreasonably or vexatiously) require to have produced for his inspection the |  |  |  | added to the Contract Sum. If any loss or damage affecting the Works or |  |  |  | and the Employer may deduct such sum from any monies due or to become |  |  |  |  | these Conditions (including making good in consequence of such
policy and receipts in question. |  |  |  | any part thereof or any such unfixed materials or goods is occasioned by |  |  |  | due to the Contractor under this Contract. |  |  |  |  | opening up or testing), unless the inspection or test showed that the
(2) |  |  |  | anyone or more of the said contingencies then, upon discovering the said | [8 empty] | work, materials or goods were not in accordance with this Contract; or
Upon acceptance of any claim under the insurances aforesaid the |  |  |  | loss or damage the Contractor shall forthwith give notice in writing both to | [7 empty] | (c) | Any discrepancy in or divergence between the Contract Drawings and/
Contractor with due diligence shall restore work damaged, replace or repair |  |  |  | the Architect and to the Employer of the extent, nature and location thereof |  |  |  | 23 | Extension of Time |  |  |  | or the Specification; or
any unfixed materials or goods which have been destroyed or injured, |  |  |  | and |  |  |  | Upon it becoming reasonably apparent that the progress of the Works is |  |  |  | (d) | Delay on the part of artists, tradesmen or others engaged by the
remove and dispose of any debris and proceed with the carrying out and |  |  |  | (a) | the occurrence of such loss or damage shall be disregarded in |  |  | delayed, the Contractor shall forthwith give written notice of the cause of the |  |  |  |  | Employer in executing work not forming part of this Contract; or
completion of the Works. All monies received from such insurances (less |  |  |  |  | computing any amounts payable to the Contractor under or by virtue of |  |  | delay to the Architect, and if in the opinion of the Architect the completion of |  |  |  | (e) | Architect's instructions issued in regard to the postponement of any
only the aforesaid percentage (if any)) shall be paid to the Contractor by |  |  |  |  | this Contract. |  |  | the Works is likely to be or has been delayed beyond the Date for |  |  |  |  | work to be executed under the provisions of this Contract; and if the
instalments under certificates of the Architect issued at the period of Interim |  |  |  | (b) | (i) | If it is just and equitable so to do the employment of the |  | Completion stated in the Appendix to these Conditions or beyond any |  |  |  |  | written application is made within a reasonable time of it becoming
Certificates named in the Appendix to these Conditions. The Contractor | [5 empty] | Contractor under this Contract may within 28 days of the |  | extended time previously fixed under this clause, |  |  |  |  | apparent that the progress of the Works or of any part thereof has
shall not be entitled to any payment in respect of the restoration of work | [5 empty] | occurrence of such loss or damage be determined at the option |  | (a) | by force majeure, or |  |  |  | been affected as aforesaid, then the Architect shall either himself
damaged, the replacement and repair of any unfixed materials or goods, & | [5 empty] | of either party by notice by registered post or recorded delivery |  | (b) | by reason of any exceptionally inclement weather, or |  |  |  | ascertain or shall instruct the Quantity Surveyor to ascertain the
the removal & disposal of debris other than the monies received under the | [5 empty] | from either party to the other. Within 7 days of receiving such a |  | (c) | by reason of loss or damage occasioned by anyone or more of the |  |  |  | amount of such loss and/or expense. Any amount from time to time so
said insurances. | [5 empty] | notice (but not thereafter) either party may give to the other a |  |  | contingencies referred to in clause 20(A), (B), or (C) of these |  |  |  | ascertained shall be added to the Contract Sum, and if an Interim
[6 empty] | written request to concur in the appointment of an arbitrator |  |  | Conditions, or |  |  |  | Certificate is issued after the date of ascertainment any such amount
20[B] |  | (9) |  |  |  | under clause 33 of these Conditions in order that it may be |  | (d) | by reason of civil commotion, local combination of workmen, strike or |  |  |  | shall be added to the amount which would otherwise be stated as due
All work executed and all unfixed materials and goods, delivered to, placed | [5 empty] | determined whether such determination will be just and |  |  | lockout affecting any of the trades employed upon the Works or any |  |  |  | in such Certificate.
on or adjacent to the Works and intended therefore (except temporary | [5 empty] | equitable. |  |  | of the trades engaged in the preparation, manufacture or |  |  | (2)
buildings, plant, tools and equipment owned or hired by the Contractor or |  |  |  |  | (ii) | Upon the giving or receiving by the Employer of such a notice |  |  | transportation of any of the goods or materials required for the Works, |  |  | The provisions of this Condition are without prejudice to any other rights &
any sub-contractor) shall be at the sole risk of the Employer as regards loss | [5 empty] | of determination or, where a reference to arbitration is made as |  |  | or by reason of Architect's instructions issued under clauses 1 (2), |  |  | remedies which the Contractor may possess.
or damage by fire, lightning, explosion, storm, tempest, bursting or | [5 empty] | aforesaid, upon the arbitrator upholding the notice of |  |  | 11(1) or 21(2) of these Conditions, or by reason of the Contractor not
overflowing of water tanks, apparatus or pipes, earthquake, aircraft & other | [5 empty] | determination, the provisions of sub-clause (2) (except sub - |  |  | having received in due time necessary instructions, |  |  | 25 Determination by Employer | Determination by Employer
aerial devices or articles dropped therefrom, riot and civil commotion | [5 empty] | paragraph (vi) of paragraph (b» of clause 26 of these |  | (e) | by reason of Architect's instructions issued under clauses 1(2), 11(1) |  |  | (1)
(excluding any loss or damage caused by ionising radiations or | [5 empty] | Conditions shall apply. |  |  | or 21(2) of these Conditions, or |  |  | Without prejudice to any other rights or remedies which the Employer may
contamination by radioactivity from any nuclear fuel or from any nuclear |  |  |  | (c) | If no notice of determination is served as aforesaid, or, where a |  |  | (f) | by reason of the Contractor not having received in due time necessary |  |  | possess, if the Contractor shall make default in anyone or more of the
waste from the combustion or nuclear fuel, radioactive toxic explosive or |  |  |  |  | reference to arbitration is made as aforesaid, if the arbitrator decides |  |  |  | instructions,drawings, details or levels from the Architect for which he |  |  | following respects, that is to say:
other hazardous properties of any explosive nuclear assembly or nuclear |  |  |  |  | against the notice of determination, then |  |  |  | specifically applied in writing on a date which having regard to the Date |  |  | (a) | If he without reasonable cause wholly suspends the carrying out of the
component thereof, pressure waves caused by aircraft or other aerial |  |  |  |  | (i) | the Contractor with due diligence shall reinstate or make good |  |  | of Completion stated in the Appendix to these Conditions or to any |  |  |  | Works before completion thereof, or
devices travelling at sonic or supersonic speeds). | [5 empty] | such loss or damage, and proceed with the carrying out and |  |  | extension of time then fixed under this clause was neither
[6 empty] | completion of the Works; |  |  | unreasonably distant from nor unreasonably close to the date on which |  |  | (b) | If he fails to proceed regularly and diligently with the Works, or
The Employer shall maintain a proper policy of insurance8 against that risk, | [8 empty] | it was necessary for him to receive the same, or
& such policy and the receipt for the last premium paid for its renewal shall |  |  |  | 7 | Clause 20[A] is applicable to the erection of a new building if the |  |  | (g) | by delay on the part of nominated sub-contractors or nominated |  |  | (c) | If he refuses or persistently neglects to comply with a written notice
upon request be produced for inspection by the Contractor. If the Employer |  |  |  | Contractor is required to insure against loss or damage by fire, etc.; clause |  |  |  |  | suppliers which the Contractor has taken all practicable steps to avoid |  |  |  | from the Architect requiring him to remove defective work or improper
shall at any time fail upon request to produce any receipt showing such a |  |  |  | 20[B] is applicable to the erection of a new building if the Employer is to |  |  |  |  | or reduce, or |  |  |  | materials or goods and by such refusal or neglect the Works are
policy as aforesaid to be effective then the Contractor may in the name and |  |  |  | bear the risk in respect loss or damage by fire, etc.; and clause 20[C] is |  |  |  | (h) | by delay on the part of artists, tradesmen or others engaged by the |  |  |  | materially affected, or
on behalf of the Employer insure all work executed and all unfixed materials |  |  |  | applicable to alterations of or extensions to an existing building; therefore |  |  |  |  | Employer in executing work not forming part of this Contract, or |  |  | (d) | If he fails to comply with the provisions of clause 17 of these
and goods as aforesaid against loss or damage occasioned by the said |  |  |  | strike out clauses [B] and [C] or clauses [A] and [C] or clauses [A] and [8] as |  |  |  | (i) | by reason of the opening up for inspection of any work covered up or |  |  |  | Conditions, then the Architect may give to him a notice by registered
contingencies and shall upon production of the receipt for any premium paid |  |  |  | the case may require. |  |  |  |  | of the testing of any of the work materials or goods in accordance |  |  |  | post or recorded delivery specifying the default, and if the Contractor
by him be entitled to have its amount added to the Contract Sum. If any loss | [8 empty] | with clause 6 (3) of these Conditions (including making good in |  |  |  | either shall continue such default for fourteen days after receipt of
or damage affecting the Works or any part thereof or any such unfixed |  |  |  | 8 | In some cases it may not be possible for insurance to be taken out against |  |  |  | consequences of such opening up or testing), unless the inspection or |  |  |  | such notice or shall at any time thereafter repeat such default (whether
materials or goods is occasioned by anyone or more of the said |  |  |  | certain of the risks mentioned in this clause; in others insurance may be |  |  |  |  | test showed that the work materials or goods were not in accordance |  |  |  | previously repeated or not), then the Employer may within ten days
contingencies then, upon discovering the said loss or damage the |  |  |  | required against risks not mentioned. This matter should be arranged |  |  |  |  | with this Contract, or |  |  |  | after such continuance or repetition by notice by registered post or
Contractor shall forthwith give notice in writing both to the Architect and to |  |  |  | between the parties at the tender stage and the clauses amended |  |  |  |  | (10) |  |  |  | recorded delivery forthwith determine the employment of the
the Employer of the extent, nature and location thereof and |  |  |  | accordingly. |  |  |  | (j) | (i) | by the Contractor's inability for reasons beyond his control and |  |  | Contractor under this Contract, provided that such notice shall be
[10 empty] | which he could not reasonably have foreseen at the date of this |  |  | given unreasonably or vexatiously.
(a) | The occurrence of such loss or damage shall be disregarded in |  |  | 9 | Clause 20[AJ is a pplicable to the erection of a new building if the |  |  |  |  | Contract to secure such labour as is essential to the proper |  | (2)
| computing any amounts payable to the Contractor under or by virtue of |  |  | Contractor is required to insure against loss or damage by fire, etc.; clause | [5 empty] | carrying out of the Works, or |  | In the event of the Contractor becoming bankrupt or making a composition
| this Contract. |  |  | 20[BJ is applicable to the erection of a new building if the Employer is to |  |  |  |  | (ii) | by the Contractor's inability for reasons beyond his control and |  | or arrangement with his creditors or having a winding up order made or
|  |  |  | bear the risk in respect loss or damage by fire, etc.; and clause 20[CJ is | [5 empty] | which he could not reasonably have foreseen at the date of this |  | (except for purposes of reconstruction) a resolution for voluntary winding up
(b) | The Contractor with due diligence shall restore work damaged, |  |  | applicable to alterations of or extensions to an existing building; therefore | [5 empty] | Contract to secure such goods and/or materials as are |  | passed or a provisional liquidator receiver or manager of his business or
| replace or repair any unfixed materials or goods which have been |  |  | strike out clauses [B] and [C] or clauses [AJ and [C] or clauses [A] and [B] | [5 empty] | essential to the proper carrying out of the Works, or |  | undertaking duly appointed, or possession taken, by or on behalf of the
| destroyed or injured, remove and dispose of any debris and proceed |  |  | as the case may require. | [7 empty] | holders of any debentures secured by a floating charge, of any property
| with the carrying out and completion of the Works. The restoration of | [6 empty] | (k) | by reason of compliance with the provisions of Clause 32 of these |  |  | comprised in or subject to the floating charge, the employment of the
| work damaged, the replacement and repair of unfixed materials and |  |  | 10 | Strike out either or both of the sub-clauses (j) (i) or (j) (ii) if not to apply. |  |  |  | Conditions or with Architect's instructions issued thereunder, or |  |  | Contractor under this Contract shall be forthwith automatically determined
Copyright reserved in all drawings and the | [5 empty] | EMPLOYER | CONTRACTOR |  | PROJECT |  | SHEET TITLE |  |  | DESIGN | : SP | PROJECT NO. | 1
work executed from them. Figured dimensions | [8 empty] | test2 |  | FIJI STANDARD FORM OF
shall be read in preferance. Largest scaled | [10 empty] | BUILDING CONTRACT |  |  | PREP BY | admin | SHEET NO. | BC04
drawings shall take precedence. Check all |  |  | ARCHITECTS,DESIGN CONSULTANTS,PROJECT MANAGERS,INTERIOR DESIGNERS 26 MARA ROAD , P.O.BOX 16 , NAUSORI , FIJI ISLANDS PH.- 3400 287 , Email : designhut@connect.com.fj |  |  | WITNESS | WITNESS
dimensions on site. All discrepancies shall | [8 empty] | test |  | WITHOUT QUANTITIES |  |  | DATE | 02-09-2021 | REV:
be reported to the ARCHITECT ASAP | [8 empty] | test |  | PRIVATE EDITION 1978

## BC05
but the said employment may be reinstated & continued if the Employer & | [7 empty] | (iii) | civil commotion, or | [7 empty] | (a) | Such sums shall be deemed to include 2.5% cash discount and shall | [7 empty] | become due to the nominated sub-contractor; and that if and
the Contractor his trustee in bankruptcy, liquidator, provisional liquidator | [7 empty] | (iv) | Architect's instructions issued under clauses 1(2), 11(1) or 21 | [8 empty] | be expended in favour of such persons as the Architect shall instruct, | [7 empty] | when such sums or any part thereof are released to the
receiver or manager as the case may be shall so agree. | [8 empty] | (2) of these Conditions unless caused by reason of some | [8 empty] | and all specialists or others who are nominated by the Architect are | [7 empty] | nominated sub-contractor they shall be paid in full less only a
[9 empty] | negligence or default of the Contractor, or | [8 empty] | hereby declared to be sub-contractors employed by the Contractor and | [7 empty] | discount for cash of 2.5%- if paid within 14 days of the date
(3) | [7 empty] | (v) | the Contractor not having received in due time necessary | [8 empty] | are referred to in these Conditions as 'nominated sub-contractors'. | [7 empty] | fixed for their release in the sub-contract.
In the event of the employment of the Contractor being determined as | [8 empty] | instructions, drawings, details or levels from the Architect for | [8 empty] | Provided that the Architect shall not nominate any person as a sub- | [6 empty] | (ix) | That the Architect and his representatives shall have a right of
aforesaid and so long as it has not been reinstated and continued, the | [8 empty] | which he specifically applied in writing on a date which having | [8 empty] | contractor against whom the Contractor shall make reasonable | [7 empty] | access to the workshops and other places of the nominated
following shall be the respective rights and duties of the Employer and | [8 empty] | regard to the Date of Completion stated in the appendix to | [8 empty] | objection, or (save where the Architect and Contractor shall otherwise | [7 empty] | sub-contractor as mentioned in clause 9 of these Conditions.
Contractor: | [8 empty] | these Conditions or to any extension of time then fixed under | [8 empty] | agree) who will not enter into a sub-contract which provides (inter alia): | [6 empty] | (x) | That the employment of the nominated sub-contractor under
(a) | The Employer may employ and pay other persons to carry out and | [7 empty] | clause 23 of these Conditions was neither unreasonably distant | [16 empty] | the sub-contract shall determine immediately upon the
| complete the Works & he or they may enter upon the Works & use all | [7 empty] | from nor unreasonably close to the date on which it was | [8 empty] | (i) | That the nominated sub-contractor shall carry out & complete | [6 empty] | determination (for any reason) of the Contractor's employment
| temporary buildings, plant, tools, equipment, goods and materials | [7 empty] | necessary for him to receive the same, or | [9 empty] | the subcontract Works in every respect to the reasonable | [6 empty] | under this Contract.
| intended for, delivered to and placed on or adjacent to the Works, and | [6 empty] | (vi) | delay on the part of artists, tradesmen or others engaged by | [9 empty] | satisfaction of the Contractor & of the Architect, & in conformity |  |  |  |  | (b) | The Architect shall direct the Contractor as to the total value of the
| may purchase all materials and goods necessary for the carrying out | [7 empty] | the Employer in executing work not forming part of this | [9 empty] | with all the reasonable directions and requirements of the | [5 empty] | work, materials or goods executed or supplied by a nominated sub-
| and completion of the Works. | [7 empty] | Contract, or | [9 empty] | Contractor. | [5 empty] | contractor included in the calculation of the amount stated as due in
(b) | The Contractor shall (except where the determination occurs by reason | [6 empty] | (vii) | the opening up for inspection of any work covered up or of the | [8 empty] | (ii) | That the nominated sub-contractor shall observe, perform and | [5 empty] | any certificate issued under clause 30 of these Conditions and shall
| of the bankruptcy of the Contractor or of him having a winding up order | [7 empty] | testing of any of the work materials or goods in accordance | [9 empty] | comply with all the provisions of this Contract on the part of the | [5 empty] | forthwith inform the nominated sub-contractor in writing of the amount
| made or (except for the purposes of reconstruction) a resolution for | [7 empty] | with clause 6(3) of these Conditions (including making good in | [9 empty] | Contractor to be observed, performed and complied with (other | [5 empty] | of the said total value. The sum representing such total value shall be
| voluntary winding up passed), if so required by the Employer or | [7 empty] | consequence of such opening up or testing), unless the | [9 empty] | than clause 20(A) of these Conditions, if applicable) so far as | [5 empty] | paid by the Contractor to the nominated sub-contractor within 14 days
| Architect within fourteen days of the date of determination, assign to | [7 empty] | inspection or test showed that the work materials or goods | [9 empty] | they relate and apply to the sub-contract Works or to any | [5 empty] | of receiving from the Architect the certificate less only (i) any retention
| the Employer without payment the benefit of any agreement for the | [7 empty] | were not in accordance with this Contract, | [9 empty] | portion of the same. | [5 empty] | money which the Contractor may be entitled to deduct under the terms
| supply of materials or goods and/or for the execution of any work for | [5 empty] | (d) | The Employer becomes bankrupt or makes a composition or | [9 empty] | (iii) | That the nominated sub-contractor shall indemnify the | [5 empty] | of the sub-contract, (ii) any sum to which the Contractor may be
| the purposes of this Contract but on the terms that a supplier or sub- | [6 empty] | arrangement with his creditors or has a winding up order made or | [10 empty] | Contractor against the same liabilities in respect of the sub - | [5 empty] | entitled in respect of delay in the completion of the sub-contract Works
| contractor shall be entitled to make any reasonable objection to any | [6 empty] | (except for the purposes of reconstruction) a resolution for voluntary | [10 empty] | contract Works as those for which the Contractor is liable to | [5 empty] | or any section thereof, and (iii) a discount for cash of 2.5%.
| further assignment thereof by the Employer. In any case the Employer | [6 empty] | winding up passed or a receiver or manager of his business or | [10 empty] | indemnify the Employer under this Contract. |  |  |  |  | (c) | Before issuing any certificate under clause 30 of these Conditions the
| may pay any supplier or sub-contractor for any materials or goods | [6 empty] | undertaking is duly appointed, or possession is taken by or on behalf | [9 empty] | (iv) | That the nominated sub-contractor shall indemnify the | [5 empty] | Architect may request the Contractor to furnish to him reasonable
| delivered or works executed for the purposes of this Contract (whether | [6 empty] | of the holders of any debentures secured by a floating charge, of any | [10 empty] | Contractor against claims in respect of any negligence, | [5 empty] | proof that all amounts included in the calculation of the amount stated
| before or after the date of determination) in so far as the price thereof | [6 empty] | property comprised in or subject to the floating charge, then the | [10 empty] | omission or default of such sub-contractor, his servants or | [5 empty] | as due in previous certificates in respect of the total of the work,
| has not already been paid by the Contractor. The Employer's rights | [6 empty] | Contractor may there upon by notice by registered post or recorded | [10 empty] | agents or any misuse by him or them of any scaffolding or | [5 empty] | materials or goods executed or supplied by any nominated sub-
| under this paragraph are in addition to his rights to pay nominated | [6 empty] | delivery to the Employer or Architect forthwith determine the | [10 empty] | other plant, and shall insure himself against any such claims | [5 empty] | contractor have been duly discharged, and if the Contractor fails to
| sub-contractors as provided in clause 27(c) of these Conditions and | [6 empty] | employment of the Contractor under this Contract; provided that such | [10 empty] | and produce the policy or policies and receipts in respect of | [5 empty] | comply with any such request the Architect shall issue a certificate to
| payments made under this paragraph may be deducted from any sum | [6 empty] | notice shall not be given unreasonably or vexatiously. | [10 empty] | premiums paid as and when required by either the Architect or | [5 empty] | that effect and thereupon the Employer may himself pay such amounts
| due or to become due to the Contractor. | [5 empty] | (2) | [11 empty] | the Contractor. | [5 empty] | to any nominated sub-contractor concerned and deduct the same from
(c) | The Contractor shall as and when required in writing by the Architect | [5 empty] | Upon such determination, then without prejudice to the accrued rights or | [10 empty] | (v) | That the sub-contract Works shall be completed within the | [5 empty] | any sums due or to become due to the Contractor.
| so to do (but not before) remove from the Works any temporary | [5 empty] | remedies of either party or to any liability of the classes mentioned in clause | [11 empty] | period or (where they are to be completed in sections) periods |  |  |  |  | (d) | (i) | The Contractor shall not grant to any nominated sub-contractor
| buildings, plant, tools, equipment, goods and materials belonging to or | [5 empty] | 18 of these Conditions which may accrue either before the Contractor or | [11 empty] | therein. specified, that the Contractor shall not without the | [6 empty] | any extension of the period within which the sub-contract Works
| hired by him. If within a reasonable time after any such requirement | [5 empty] | any sub-contractors shall have removed his temporary buildings, plant, | [11 empty] | written consent of the Architect grant any extension of time for | [6 empty] | or (where the sub-contractor Works to be completed in sections)
| has been made the Contractor has not complied therewith then the | [5 empty] | tools, equipment, goods or materials or by reason of his or their so | [11 empty] | the completion of the sub-contract Works or any section | [6 empty] | any section thereof is to be completed without the written
| Employer may (but without being responsible for any loss or damage) | [5 empty] | removing the same, the respective rights and liabilities of the Contractor & | [11 empty] | thereof, & that the Contractor shall inform the Architect of any | [6 empty] | consent of the Architect, provided always that the Contractor
| remove and sell any such property of the Contractor, holding the | [5 empty] | the Employer shall be as follows, that is to say: | [11 empty] | representation made by the nominated sub-contractor as to the | [6 empty] | shall inform the Architect of any representations made by the
| proceeds less all cost incurred to the credit of the Contractor. | [5 empty] | (a) | The Contractor shall with all reasonable dispatch and in such manner | [10 empty] | cause of any delay in the progress or completion of the sub- | [6 empty] | nominated sub-contractor as to the cause of any delay in the
(d) | The Contractor shall allow or pay to the Employer in the manner | [6 empty] | and with such precautions as will prevent injury, death or damage of | [10 empty] | contract Works or of any section thereof. | [6 empty] | progress or completion of the sub-contract Works or of any
| hereinafter appearing the amount of any direct loss and/ or damage | [6 empty] | the classes in respect of which before the date of determination he | [9 empty] | (vi) | That if the nominated sub-contractor shall fail to complete the | [6 empty] | section thereof, and that the consent of the Architect shall not be
| caused to the Employer by the determination. Until after completion of | [6 empty] | was liable to indemnify the Employer under clause 18 of these | [10 empty] | sub-contract Works or (where the sub-contract Works are to be | [6 empty] | unreasonably withheld.
| the Works under paragraph (a) of this sub-clause the Employer shall | [6 empty] | Conditions remove from the site all his temporary buildings, plant, | [10 empty] | completed in sections) any section thereof within the period | [5 empty] | (ii) | If any nominated sub-contractor fails to complete the sub-
| not be bound by any provision of this Contract to make any further | [6 empty] | tools, equipment, goods and materials and shall give facilities for his | [10 empty] | therein specified or within any extended time granted by the | [6 empty] | contract Works or (where the sub-contract Works are to be
| payment to the Contractor, but upon such completion and the | [6 empty] | sub-contractors to do the same, but subject always to the provisions | [10 empty] | Contractor with the written consent of the Architect, and the | [6 empty] | completed in sections) any section thereof within the period
| verification within a reasonable time of the accounts therefore the | [6 empty] | of sub-paragraph (iv) of paragraph (b) of this sub-clause | [10 empty] | Architect certifies in writing to the Contractor that the same | [6 empty] | specified in the sub-contract or within any extended time granted
| Architect shall certify the amount of expenses properly incurred by the | [5 empty] | (b) | After taking into account amounts previously paid under this Contract | [10 empty] | ought reasonably so to have been completed, the nominated | [6 empty] | by the Contractor with the written consent of the Architect, then if
| Employer and the amount of any direct loss and/ or damage caused to | [6 empty] | the Contractor shall be paid by the Employer: | [10 empty] | sub-contractor shall pay or allow to the Contractor either a sum | [6 empty] | the same ought reasonably so to have been completed the
| the Employer by the determination and, if such amounts when added | [6 empty] | (i) | The total value of work completed at the date of determination. | [9 empty] | calculated at the rate therein agreed as liquidated and | [6 empty] | Architect shall certify in writing accordingly; immediately upon
| to the monies paid to the Contractor before the date of determination | [6 empty] | (ii) | The total value of work begun and executed but not completed | [9 empty] | ascertained damages for the period during which the said | [6 empty] | issue the Architect shall send a duplicate of any such certificate
| exceed the total amount which would have been payable on due | [7 empty] | at the date of determination, the value being ascertained in | [9 empty] | Works or any section thereof, as the case may be, shall so | [6 empty] | to the nominated sub-contractor.
| completion in accordance with this Contract, the difference shall be a | [7 empty] | accordance with clause 11(4) of these Conditions as if such | [9 empty] | remain or have remained incomplete or (where no such rate is |  |  |  |  | (e) | If the Architect desires to secure final payment to any nominated sub-
| debt payable to the Employer by the Contractor; & if the said amounts | [7 empty] | work were a variation required by the Architect. | [9 empty] | therein agreed) a sum equivalent to any loss or damage | [5 empty] | contractor before final payment is due to the Contractor, & if such sub-
| when added to the said monies be less than the said total amount, the | [6 empty] | (iii) | Any sum ascertained in respect of direct loss and/or expense | [9 empty] | suffered or incurred by the Contractor and caused by the failure | [5 empty] | contractor has satisfactorily indemnified the Contractor against any
| difference shall be a debt payable by the Employer to the Contractor. | [7 empty] | under clauses 11(6), 24 & 32(3) of these Conditions (whether | [9 empty] | of the nominated sub-contractor as aforesaid. | [5 empty] | latent defects, then the Architect may in an Interim Certificate include
[9 empty] | ascertained before or after the date | [8 empty] | (vii) | That payment in respect of any work, materials or goods | [5 empty] | an amount to cover the said final payment, and thereupon the
26 Determination by Contractor | [7 empty] | (iv) | The cost of materials or goods properly ordered for the Works | [9 empty] | comprised in the subcontract shall be made within 14 days after | [5 empty] | Contractor shall pay to such nominated sub-contractor the amount so
(1) | [8 empty] | for which the Contractor shall have paid or for which the | [9 empty] | receipt by the Contractor of the Architect's certificate under | [5 empty] | certified less only a discount for cash of 2.5%. Upon such final
Without prejudice to any other rights & remedies which the Contractor may | [8 empty] | Contractor is legally bound to pay, and on such payment by the | [9 empty] | clause 30 of these Conditions which states as due an amount | [5 empty] | payment the Contractor shall, save for latent defects, be discharged
possess, if | [8 empty] | Employer any materials or goods so paid for shall become the | [9 empty] | calculated by including the total value of such work, materials | [5 empty] | from all liability for the work materials or goods executed or supplied
(a) | The Employer does not pay to the Contractor the amount due on any | [7 empty] | property of the Employer. | [9 empty] | or goods, and shall when due be subject to the retention by the | [5 empty] | by such sub-contractor under the sub-contract to which the payment
| certificate within 14 days from the presentation of that certificate and | [17 empty] | Contractor of the sums mentioned in sub-paragraph (viii) of | [5 empty] | relates.
| continues such default for seven days after receipt by registered post | [6 empty] | (v) | The reasonable cost of removal under paragraph (a) of this | [9 empty] | paragraph (a) of this Condition and to a discount for cash of |  |  |  |  | (f) | Neither the existence nor the exercise of the foregoing powers nor
| or recorded delivery of a notice from the Contractor stating that notice | [7 empty] | sub-clause. | [9 empty] | 2.5% if made within the said period of 14 days. | [5 empty] | anything else contained in these Conditions shall render the Employer
| of determination under this Condition will be served if payment is not | [6 empty] | (vi) | Any direct loss and/or damage caused to the Contractor by the | [8 empty] | (viii) | That the Contractor shall retain from the sum directed by the | [5 empty] | in any way liable to any nominated sub-contractor.
| made within seven days from receipt thereof; or | [7 empty] | determination. | [9 empty] | Architect as having been included in the calculation of the |  |  |  |  | (g) | (i) | Where the Contractor in the ordinary course of his business
(b) | The Employer interferes with or obstructs the issue of any certificate | [17 empty] | amount due in any certificate issued under clause 30 of these | [6 empty] | directly carries out works for which prime cost sums are included
| due under this Contract; or | [5 empty] | Provided that in addition to all other remedies the Contractor upon such | [11 empty] | Conditions in respect of the total value of work, materials or | [6 empty] | in the Specification and where items of such works are set out in
(c) | The carrying out of the whole or substantially the whole of the | [5 empty] | determination may take possession of and shall have a lien upon all unfixed | [11 empty] | goods executed or supplied by the nominated sub-contractor a | [6 empty] | the Appendix to these Conditions and the Architect is prepared
| uncompleted Works (other than the execution of work required under | [5 empty] | goods and materials, which may have become the property of the Employer | [11 empty] | percentage (which percentage shall be equal to the percentage | [6 empty] | to receive tenders from the Contractor for such items, then the
| clause 15 of these Conditions) is suspended for a continuous period of | [5 empty] | under clause 14 of these Conditions until payment of all monies due to the | [11 empty] | currently being retained by the Employer under clause 30 of | [6 empty] | Contractor shall be permitted to tender for the same or any of
| the length named in the Appendix to these Conditions by reason of: | [5 empty] | Contractor from the Employer. | [11 empty] | these Conditions) of such value; and that the Contractor's | [6 empty] | them but without prejudice to the Employer's right to reject the
[19 empty] | interest in any sums so retained (by whomsoever held) shall be | [6 empty] | lowest or any tender. If the Contractor's tender is accepted, he
| (i) | by force majeure, or |  |  |  |  | 27 | Nominated sub-contractors | [10 empty] | fiduciary as trustee for the nominated sub-contractor (but | [6 empty] | shall not sub-let the work without the consent of the Architect:
| (ii) | loss or damage (unless caused by the negligence of the |  |  |  |  | The following provisions of this Condition shall apply where prime cost | [11 empty] | without obligation to invest); and that the nominated sub- | [6 empty] | Provided that where a prime cost sum arises under Architect's
|  | Contractor, his servants or agents or of any sub-contractor, his |  |  |  |  | sums are included in the Specification or arise as a result of Architect's | [11 empty] | contractor's beneficial interest in such sums shall be subject | [6 empty] | instructions issued under clause 11(3) of these Conditions it
|  | servants or agents) occasioned by anyone or more of the |  |  |  |  | instructions given in regard to the expenditure of provisional sums in respect | [11 empty] | only to the right of the Contractor to have recourse thereto from | [6 empty] | shall be deemed for the purposes of this paragraph to have been
|  | contingencies referred to in clause 20(A) or clause 20(B) of |  |  |  |  | of persons to be nominated by the Architect to supply and fix materials or | [11 empty] | time to time for payment of any amount which he is entitled | [6 empty] | included in the Specification and the item of work to which it
|  | these Conditions (if applicable), or |  |  |  |  | goods or to execute work. | [11 empty] | under the sub-contract to deduct from any sum due or to | [6 empty] | relates shall likewise be deemed to have been set out in the
Copyright reserved in all drawings and the | [8 empty] | EMPLOYER |  | CONTRACTOR | [6 empty] | PROJECT |  |  | SHEET TITLE | [5 empty] | DESIGN | : SP | PROJECT NO. | 1
work executed from them. Figured dimensions | [17 empty] | test2 |  |  | FIJI STANDARD FORM OF
shall be read in preferance. Largest scaled | [20 empty] | BUILDING CONTRACT | [5 empty] | PREP BY | admin | SHEET NO. | BC05
drawings shall take precedence. Check all |  |  | ARCHITECTS,DESIGN CONSULTANTS,PROJECT MANAGERS,INTERIOR DESIGNERS 26 MARA ROAD , P.O.BOX 16 , NAUSORI , FIJI ISLANDS PH.- 3400 287 , Email : designhut@connect.com.fj | [5 empty] | WITNESS |  | WITNESS
dimensions on site. All discrepancies shall | [17 empty] | test |  |  | WITHOUT QUANTITIES | [5 empty] | DATE | 02-09-2021 | REV:
be reported to the ARCHITECT ASAP | [17 empty] | test |  |  | PRIVATE EDITION 1978
less 0.29
[24 empty] | 9 |  | 37
7 | 7 | 61.85 | 64.57 | 5 | 9.55 |  | 7 | 7 | 9.11 | 59.6 | 21.57 | 26.57 | 5 | 8.43 | 9 |  | 7 | 7 | 90 | 32.43 | 5 | 14.34 |  | 8 | 7 | 38.96 | 22 | 22 | 35 | 22
13.38
12 | 12 | 51.85 | 64.57 | 5 | 9.55 | 5 |  | 14.89 | 9.11 | 59.6 | 21.57 | 26.57 | 5 | 8.43 | 9.8 | 5 | 6.2 | 5.8 | 79.2 | 32.43 | 5 | 14.34 | 5 | 12 | 12 | 29.96 | 22 | 22 | 35 | 22 | 154.96 | 168.34
43.34
28.71 | 7.43 | 39.71 | 64.57 | 5 | 8.43 |  |  | 21 | 21.57 | 47.14 | 21.57 | 26.57 | 5 | 8.43 |  |  | 21 | 2.71 | 23.29 | 32.43 | 5 | 12.43 | 15.29 | 3.29 |  | 42.29 | 22 | 22 | 35 | 22 | 563.86
548.86
[22 empty] | 1.91 | [8 empty] | 137.215

## BC06
|  | Appendix to these Conditions. |  |  |  |  | 30 Certificates & Payments | [9 empty] | (b) | If any Interim Certificate is issued after the issue of the Certificate of | [5 empty] | (7)
| (ii) | It shall be a condition of any tender accepted under this |  |  |  |  | (1) | [10 empty] | Practical Completion but before the issue of the Certificate for the | [5 empty] | (a) | Except as provided in paragraphs (b) and (c) of this sub-clause (and
|  | paragraph that clause 11 of these Conditions shall apply in |  |  |  |  | Interim valuations shall be made whenever the Architect considers them to | [10 empty] | residue of the amounts then so retained referred to in sub-clause (4)(c) | [6 empty] | save in respect of fraud); the Final Certificate shall have effect in any
|  | respect of the items of work included in the tender as if for the |  |  |  |  | be necessary for the purpose. of ascertaining the amount to be stated as | [10 empty] | of this Condition the Employer in respect of the said Interim Certificate | [6 empty] | proceedings arising out of or in connection with this Contract (whether
|  | reference therein to the Contract Drawings & the Specification |  |  |  |  | due in an Interim Certificate. The Architect shall from time to time as | [10 empty] | may, subject to paragraph (c) of this sub-clause, retain a percentage | [6 empty] | by arbitration under clause 33 of these Conditions or otherwise) as
|  | there were references to the equivalent documents included in |  |  |  |  | provided in this sub-clause issue Interim Certificates stating the amount due | [10 empty] | (which percentage shall be equal to half the Retention Percentage) of | [6 empty] | (i) | conclusive evidence that where the quality of materials or the
|  | or referred to in the tender. |  |  |  |  | to the Contractor from the Employer, and the Contractor shall be entitled to | [10 empty] | the total value of the work, materials & goods referred to in sub- | [7 empty] | standards of workmanship are to be to the reasonable
28 | Nominated Suppliers | [5 empty] | payment therefor within 14 days from the presentation of that Certificate. | [10 empty] | clauses (2) and (2A) of this Condition. | [7 empty] | satisfaction of the Architect the same are to such satisfaction,
The following provisions of this Condition shall apply where prime cost | [6 empty] | Before the issue of the Certificate of Practical Completion, Interim | [9 empty] | (c) | The amount which the Employer may retain by virtue of paragraphs | [7 empty] | and
sums are included in the Specification, or arise as a result of Architect's | [6 empty] | Certificates shall be issued at the Period of Interim Certificates specified in | [10 empty] | (a) and/or (b) of this sub-clause shall be reduced by the amounts of | [6 empty] | (ii) | conclusive evidence that any necessary effect has been given
instructions given in regard to the expenditure of provisional sum, in respect | [6 empty] | the Appendix to these Conditions. After the issue of the Certificate of | [10 empty] | any releases of retention made to the Contractor in pursuance of | [7 empty] | to all the terms of this Contract which require an adjustment to
of any materials or goods to be fixed by the Contractor. | [6 empty] | Practical Completion, Interim Certificates shall be issued as & when further | [10 empty] | Clause 16(f) and/or clause 27(e) of these Conditions. | [7 empty] | be made of the Contract Sum save where there has been any
(a) | Such sums shall be deemed to include 5% cash discount and the term | [5 empty] | amounts are due to the Contractor from the Employer provided always that | [9 empty] | (4) | [8 empty] | accidental inclusion or exclusion of any work, materials, goods
| prime cost when included or arising as aforesaid, shall be understood | [5 empty] | the Architect shall not be required to issue an Interim Certificate within one | [9 empty] | The amounts retained by virtue of sub-clause (3) of this Condition shall be | [8 empty] | or figure in any computation or any arithmetical error in any
| to mean the net cost to be defrayed as a prime cost after deducting | [5 empty] | calendar month of having issued a previous Interim Certificate. | [9 empty] | subject to the following rules: | [8 empty] | computation, in which event the Final Certificate shall have
| any trade or other discount (except the said discount of 5%), & shall | [5 empty] | (2) | [9 empty] | (a) | The Employer's interest in any amounts so retained shall be fiduciary | [7 empty] | effect as conclusive evidence as to all other computations.
| include any tax or duty not otherwise recoverable under this contract | [5 empty] | The amount stated as due in an Interim Certificate shall, subject to any | [10 empty] | as trustee for the Contractor (but without obligation to invest), and the | [5 empty] | (b) | If any arbitration or other proceedings have been commenced by either
| by whomsoever payable which is payable under or by virtue of any Act | [5 empty] | agreement between the parties as to stage payments, be the total value of | [10 empty] | Contractor's beneficial interest therein shall be subject only to the right | [6 empty] | party before the Final Certificate has been issued the Final Certificate
| of Parliament on the import, purchase, sale, appropriation, processing, | [5 empty] | the work properly executed and of the materials and goods delivered to or | [10 empty] | of the Employer to have recourse thereto from time to time for | [6 empty] | shall have effect as conclusive evidence as provided in paragraph (a)
| alteration, adapting for sale or use of the materials or goods to be | [5 empty] | adjacent to the Works for use thereon up to and including a date not more | [10 empty] | payment of any amount which he is entitled under the provisions of this | [6 empty] | of this sub-clause after either
| supplied, and the cost of packing, carriage and delivery. Provided that, | [5 empty] | than seven days before the date of the said certificate less any amount | [10 empty] | Contract to deduct from any sum due or to become due to the | [6 empty] | (i) | such proceedings have been concluded, whereupon the Final
| where in the opinion of the Architect the Contractor has incurred | [5 empty] | which may be retained by the Employer (as provided in sub-clause (3) of | [10 empty] | Contractor. | [7 empty] | Certificate shall be subject to the terms of any award or
| expense for special packing or special carriage, such special expense | [5 empty] | this Condition) & less any instalments previously paid under this Condition. | [9 empty] | (b) | On the issue of the Certificate of Practical Completion the Architect | [7 empty] | judgement in or settlement of such proceedings, or
| shall be allowed as part of the sums actually paid by the Contractor. | [5 empty] | Provided that such certificate shall only include the value of the said | [10 empty] | shall issue a certificate for one moiety of the total amounts then so | [6 empty] | (ii) | a period of 12 months during which neither party has taken any
(b) | Such sums shall be expended in favour of such persons as the | [5 empty] | materials and goods as & from such time as they are reasonably, properly | [10 empty] | retained and the Contractor shall, on presenting any such certificate to | [7 empty] | further step in such proceedings, whereupon the Final
| Architect shall instruct, and all specialists, merchants, tradesmen or | [5 empty] | & not prematurely brought to or placed adjacent to the Works and then only | [10 empty] | the Employer, be entitled to payment of the said moiety within 14 days | [7 empty] | Certificate shall be subject to any terms agreed in partial
| others who are nominated by the Architect to supply materials or | [5 empty] | if adequately protected against weather or other casualties. | [10 empty] | from the presentation of that certificate. | [7 empty] | settlement,
| goods are hereby declared to be suppliers to the Contractor and are | [5 empty] | (2A) | [9 empty] | (5) | [7 empty] | which ever shall be the earlier.
| referred to in these Conditions as 'nominated suppliers'. Provided that | [5 empty] | The amount stated as due in an Interim Certificate may at the discretion of | [9 empty] | (a) | The measurement and valuation of the Works shall be completed | [5 empty] | (c) | If any arbitration or other proceedings have been commenced by either
| the Architect shall not (save where the Architect and Contractor shall | [5 empty] | the Architect include the value of any materials or goods before delivery | [10 empty] | within the Period of Final Measurement and Valuation stated in the | [6 empty] | party within 14 days after the Final Certificate has been issued, the
| otherwise agree) nominate as a supplier a person who will not enter | [5 empty] | thereof to or adjacent to the Works provided that: | [10 empty] | Appendix to these Conditions, & the Contractor shall be supplied with | [6 empty] | Final Certificate shall have effect as conclusive evidence as provided
| into a contract of sale which provides (inter alia): | [16 empty] | a copy of the priced Bills of Variation not later than the end of the said | [6 empty] | in paragraph (a) of this sub-clause save only in respect of all matters
| (i) | That the materials or goods to be supplied shall be to the |  |  |  |  | (a) | Such materials or goods are intended for inclusion in the Works; | [9 empty] | Period & before the issue of the Final Certificate under sub-clause (6) | [6 empty] | to which those proceedings relate.
|  | reasonable satisfaction of the Architect. |  |  |  |  | (b) | Nothing remains to be done to such materials or goods to complete | [9 empty] | of this Condition. | [5 empty] | (8)
| (ii) | That the nominated supplier shall make good by replacement | [5 empty] | the same up to the point of their incorporation in the Works; | [8 empty] | (b) | Either before or within a reasonable time after Practical Completion of | [5 empty] | Save as aforesaid no certificate of the Architect shall of itself be conclusive
|  | or otherwise any defects in the materials or goods supplied |  |  |  |  | (c) | Such materials or goods have been and are set apart at the premises | [9 empty] | the Works the Contractor shall send to the Architect all documents | [5 empty] | evidence that any works materials or goods to which it relates are in
|  | which appear within such period as is therein mentioned & shall | [5 empty] | where they have been manufactured or assembled or are stored, and | [9 empty] | necessary for the purposes of the computations required by these | [5 empty] | accordance with this Contract.
|  | bear any expenses reasonably incurred by the Contractor as a | [5 empty] | have been clearly and visibly marked, individually or in sets, either by | [9 empty] | Conditions including all documents relating to the accounts of | [5 empty] | 31A |  | Fluctuations (12)
|  | direct consequence of such defects, provided that: | [5 empty] | letters or figures or by reference to a pre-determined code, so as to | [9 empty] | nominated sub-contractors and nominated suppliers. | [5 empty] | The Contract Sum shall be deemed to have been calculated in the manner
| (1) | where the materials or goods have been used or fixed such | [5 empty] | identify; | [8 empty] | (c) | In the settlement of accounts the amounts paid or payable under the | [5 empty] | set out below and shall be subject to adjustment in the events specified
|  | defects are not such that examination by the Contractor | [5 empty] | (i) | Where they are stored on premises of the Contractor, the | [8 empty] | appropriate contracts by the Contractor to nominated sub-contractors | [5 empty] | hereunder:
|  | ought to have revealed them before using or fixing; | [6 empty] | Employer, and in any other case, the person to whose order | [8 empty] | or nominated suppliers (including the discounts fox' cash mentioned in | [5 empty] | (a) | (i) | The prices (including the cost of workmen's compensation & of
| (2) | such defects are due solely to defective workmanship or | [6 empty] | they are held; and | [8 empty] | clauses 27 and 28 of the Conditions), the amounts paid or payable by | [7 empty] | third party insurance) contained in the Schedule of Rates are
|  | materials in the goods supplied and shall not have been | [5 empty] | (ii) | Their destination as being the Works; | [8 empty] | virtue of clause 4(2) of these Conditions in respect of fees or charges, | [7 empty] | based upon the rates of wages and the other emoluments and
|  | caused by improper storage by the Contractor or by misuse |  |  |  |  | (d) | Where such materials or goods were ordered from a supplier by the | [9 empty] | the amounts paid or payable in respect of any insurances maintained | [7 empty] | expenses which will be payable by the Contractor to or in
|  | or by any act or neglect of either the Contractor, Architect or | [5 empty] | Contractor or a subcontractor, the contract for their supply is in writing | [9 empty] | in compliance with clause 19(2) of these Conditions is accepted & the | [7 empty] | respect of work people engaged upon or in connection with the
|  | the Employer or by any person or persons for whom they | [5 empty] | & expressly provides that the property therein shall pass | [9 empty] | value of any work executed by the Contractor for which a provisional | [7 empty] | Works in accordance with the visions of the Wages Regulation
|  | may be responsible. | [5 empty] | unconditionally to the Contractor or the sub-contractor (as the case | [9 empty] | sum is included in the Specification shall be set against the relevant | [7 empty] | (Building and Civil and Electrical Engineering Trades) Order
| (iii) | That delivery of the materials or goods supplied shall be | [5 empty] | may be) not later than the happening of the events set out in | [9 empty] | prime cost or provisional sum mentioned in the Specification or arising | [7 empty] | which will be applicable to the Works and which have been
|  | commenced and completed at such times as the Contractor | [5 empty] | paragraphs (b) and (c) of this sub-clause; | [9 empty] | under Architect's instructions issue under clause 11(3) of these | [7 empty] | promulgated at the date of tender, or in the case of work
|  | may reasonably direct. |  |  |  |  | (e) | Where such materials or goods were ordered from a supplier by the | [9 empty] | Conditions as the case may be, and the balance, after allowing in all | [7 empty] | people so engaged whose rates of wages and other
| (iv) | That the nominated supplier shall allow the Contractor a | [5 empty] | sub-contractor, the relevant sub-contract is in writing and expressly | [9 empty] | cases pro rata for the Contractor's profit at the rates shown in the | [7 empty] | emoluments and expenses are governed by the provisions of
|  | discount for cash of 5% if the Contractor makes payment in | [5 empty] | provides that on the property in such materials or goods passing to the | [9 empty] | Schedule of rates, shall be added to or deducted from the Contract | [7 empty] | some other wages regulation order or by the terms of an
|  | full within 30 days of the end of the month during which | [5 empty] | sub-contract the same shall immediately thereon pass to the | [9 empty] | Sum. Provided that no deduction shall be made in respect of any | [7 empty] | agreement between the Contractor and a registered and
|  | delivery is made. | [5 empty] | Contractor; | [9 empty] | damages paid or allowed to the Contractor by any sub-contractor or | [7 empty] | recognised trade union, in accordance with the provisions or
| (v) | That the nominated supplier shall not be obliged to make any |  |  |  |  | (f) | Where such materials or goods were manufactured or assembled by a | [9 empty] | supplier. | [7 empty] | terms of such other wages regulation order or agreement which
|  | delivery of materials or goods (except any which may have | [5 empty] | sub-contractor the sub-contract is in writing and expressly provides | [8 empty] | (6) | [8 empty] | will be applicable and which have been promulgated as
|  | been paid for in full, less only the discount for cash) after the | [5 empty] | that the property in such materials or goods shall pass unconditionally | [8 empty] | So soon as is practicable but before the expiration of 3 months from the end | [8 empty] | aforesaid. (13)
|  | determination (for any reason) of the Contractor's employment | [5 empty] | to the Contractor not later than the happening of the events set out in | [8 empty] | of the Defects Liability Period stated in the Appendix to these Conditions or | [7 empty] | (ii) | If any of the said rates of wages or other emoluments and
|  | under this Contract. | [5 empty] | paragraphs (b) and (c) of this sub-clause. | [8 empty] | from completion of making good defects under clause 15 of these | [8 empty] | expenses are increased or decreased by reason of any
(c) | All payments by the Contractor for materials or goods supplied by a | [5 empty] | (g) | The materials or goods are in accordance with this Contract; | [8 empty] | Conditions or from receipt by the Architect of the documents referred to in | [8 empty] | alteration in the said provisions or terms promulgated after the
| nominated supplier shall be in full & shall be paid within 30 days of the | [5 empty] | (h) | The Contractor furnishes to the Architect reasonable proof that the | [8 empty] | paragraph (b) of sub-clause (5) of this Condition,whichever is the latest, the | [8 empty] | date of tender, then the net amount of the increase / decrease
| end of the month during which delivery is made less only a discount | [6 empty] | property in such materials or goods is in him and that the appropriate | [8 empty] | Architect shall issue the Final Certificate. The Final Certificate shall state: | [8 empty] | in wages and other emoluments and expenses together with
| for cash of 5% if so paid. | [6 empty] | conditions set out in paragraphs (a) to (g) of this sub-clause have been | [8 empty] | (a) | The sum of the amounts already paid to the Contractor under Interim | [7 empty] | the net amount of any consequential increase or decrease in
(d) | Where the said contract of sale between the Contractor and the | [6 empty] | complied with; | [9 empty] | Certificates and Certificates issued under sub-clauses (4)(b) and (4)(c) | [7 empty] | the cost of workmen's compensation insurance, of third party
| nominated supplier in any way restricts, limits or excludes the liability | [5 empty] | (i) | The Contractor furnishes the Architect with reasonable proof that such | [9 empty] | of this Condition, and
| of the nominated supplier to the Contractor in respect of materials or | [6 empty] | materials or goods are insured against loss or damage for their full | [8 empty] | (b) | The Contract Sum adjusted as necessary in accordance with the terms
| goods supplied or to be supplied, and the Architect has specifically | [6 empty] | value under a policy of insurance protecting the interest of the | [9 empty] | of these Conditions,
| approved in writing the said restrictions, limitations or exclusions, the | [6 empty] | Employer and the Contractor in respect of the contingencies referred | [8 empty] | and the difference (if any) between the two sums shall be expressed in the | [6 empty] | (12) Parts A, C, V and E should be used where the parties have agreed to
| liability of the Contractor to the Employer in respect of the said | [6 empty] | to in clause 20 of these Conditions, during the period commencing with | [8 empty] | said certificate as a balance due to the Contractor from the Employer or to | [6 empty] | allow the labour and materials cost and tax fluctuations to which Part A
| materials or goods shall be restricted, limited or excluded to the same | [6 empty] | the transfer of property in such materials or goods to the Contractor | [8 empty] | the Employer from the Contractor as the case may be. Subject to any | [6 empty] | refers. Otherwise Parts B, C, V, and E should be used.
| extent. The Contractor shall not be obliged to enter into a contract with, | [6 empty] | until they are delivered to, or adjacent to, the Works. | [8 empty] | deductions authorised by these Conditions, the said balance as from the | [6 empty] | (13) The terms of any such agreement, or any subsequent alteration thereto,
| nor expend prime cost sums in favour ot the nominated supplier until | [5 empty] | (3) | [9 empty] | 14th day after presentation of the Final Certificate by the Contractor to the | [6 empty] | shall be those established by machinery of negotiation or arbitration to
| the Architect has specifically approved in writing the said restrictions, | [6 empty] | (a) | In respect of any Interim Certificate issued before the issue of the | [7 empty] | Employer shall be a debt payable by the Employer to the Contractor or as | [6 empty] | which the parties are an organisation of employers & a trade union
| limitations or exclusions. | [7 empty] | Certificate of Practical Completion the Employer may, subject to | [7 empty] | the case may be as from the 14th day after issue of the Final Certificate | [6 empty] | representative respectively of substantial proportions of the employers and
29 Artists & Tradesmen | [8 empty] | paragraph (c) of this sub-clause,retain a percentage (in these | [7 empty] | shall be a debt payable by the Contractor to the Employer. | [6 empty] | workers engaged in the trade or industry. If an organisation of employers is
The Contractor shall permit the execution of work not forming part of this | [8 empty] | Conditions called "the Retention Percentage") of the total value of the | [14 empty] | not itself a party to any such agreement, then its terms, or any subsequent
Contract by artists, tradesmen or others engaged by the Employer. Every | [8 empty] | work, materials and goods referred to in sub-clause (2) and (2A) of | [14 empty] | alterations thereto, shall be those endorsed by such an organisation, or, in
such person shall for the purposes of clause 18 of these Conditions be | [8 empty] | this Condition.The Retention Percentage shall be 5% unless a lower | [14 empty] | the absence of any such organisation, shall not be inconsistent with those
deemed to be a person for whom the Employer is responsible and not to be | [8 empty] | rate shall be agreed between the parties & specified in the Appendix | [7 empty] | (11) Where the Employer at tender stage estimates the Contract Sum to be | [6 empty] | observed by other employers whose general circumstances in the trade or
a sub-contractor. | [8 empty] | to these Conditions as the Retention Percentage. (11) | [7 empty] | $500,000 or over the Retention Percentage should not be more than 3%. | [6 empty] | industry in which the Contractor is engaged are similar.
Copyright reserved in all drawings and the | [8 empty] | EMPLOYER |  | CONTRACTOR | [6 empty] | PROJECT |  |  | SHEET TITLE | [5 empty] | DESIGN | : SP | PROJECT NO. | 1
work executed from them. Figured dimensions | [17 empty] | test2 |  |  | FIJI STANDARD FORM OF
shall be read in preferance. Largest scaled | [20 empty] | BUILDING CONTRACT | [5 empty] | PREP BY | admin | SHEET NO. | BC06
drawings shall take precedence. Check all |  |  | ARCHITECTS,DESIGN CONSULTANTS,PROJECT MANAGERS,INTERIOR DESIGNERS 26 MARA ROAD , P.O.BOX 16 , NAUSORI , FIJI ISLANDS PH.- 3400 287 , Email : designhut@connect.com.fj | [5 empty] | WITNESS |  | WITNESS
dimensions on site. All discrepancies shall | [17 empty] | test |  |  | WITHOUT QUANTITIES | [5 empty] | DATE | 02-09-2021 | REV:
be reported to the ARCHITECT ASAP | [17 empty] | test |  |  | PRIVATE EDITION 1978
less 0.29
[24 empty] | 9 |  | 37
7 | 7 | 61.85 | 64.57 | 5 | 9.55 |  | 7 | 7 | 9.11 | 59.6 | 21.57 | 26.57 | 5 | 8.43 | 9 |  | 7 | 7 | 90 | 32.43 | 5 | 14.34 |  | 8 | 7 | 38.96 | 22 | 22 | 35 | 22
13.38
12 | 12 | 51.85 | 64.57 | 5 | 9.55 | 5 |  | 14.89 | 9.11 | 59.6 | 21.57 | 26.57 | 5 | 8.43 | 9.8 | 5 | 6.2 | 5.8 | 79.2 | 32.43 | 5 | 14.34 | 5 | 12 | 12 | 29.96 | 22 | 22 | 35 | 22
[31 empty] | 154.96 | 168.34
43.34
28.71 | 7.43 | 39.71 | 64.57 | 5 | 8.43 |  |  | 21 | 21.57 | 47.14 | 21.57 | 26.57 | 5 | 8.43 |  |  | 21 | 2.71 | 23.29 | 32.43 | 5 | 12.43 | 15.29 | 3.29 |  | 42.29 | 22 | 22 | 35 | 22
0
[22 empty] | 1.91 | [8 empty] | -15
-3.75

## BC07
| insurance and of any contribution, levy or tax payable by a |  |  |  | (ii) | If any of the tender rates other than a rate of levy payable by |  | 31D |  |  |  | (b) | take all steps which may be necessary to preserve the object in the
| person in his capacity as an employer, shall, as the case may |  |  |  |  | virtue of the Fiji National Training Act 1973, is increased or |  | (1) |  |  |  |  | exact position and condition in which it was found; and
| be, be paid to or allowed by the Contractor. |  |  |  |  | decreased, or if a tender type ceases to be payable, or if a new |  | The Contractor shall give a written notice to the Architect of the occurrence |  |  |  | (c) | inform the Architect or the Clerk of Works of the discovery and precise
(b) | (i) | The prices contained in the Schedule of Rates are based upon |  |  |  | type of contribution, levy or tax which is payable by a person in |  | of any of the events referred to in such of the following provisions as are |  |  |  |  | location of the object.
|  | the types and rates of contribution, levy and tax payable by a |  |  |  | his capacity as an employer becomes payable after the date of |  | applicable for the purpose of this Contract: |  |  |  | (2)
|  | person in his capacity as an employer and which at the date of |  |  |  | tender, then in any such case the net amount of the difference | [5 empty] | The Architect shall issue instructions in regard to what is to be done
|  | tender are payable by the Contractor. A type and a rate so |  |  |  | between what the Contractor actually pays or will pay in |  |  | (a) | Clause 31A(a)(ii); (b) Clause 31A(b )(ii); (c) Clause 31A(b)(iv); |  | concerning an object reported by the Contractor under the preceding sub-
|  | payable are in the next sub-paragraph referred to as a 'tender |  |  |  | respect of work people whilst they are engaged upon or in |  |  | (d) | Clause 31A(c)(ii); (e) Clause 31B(a)(ii); (f) Clause 31B(a)(iv); |  | clause, & (without prejudice to the generality of this power) such instructions
|  | type' and a 'tender rate'. |  |  |  | connection with the Works, or because of his employment of |  |  | (g) | Clause 31B(b)(ii); (h) Clause 31C(2). |  | may require the Contractor to permit the examination, excavation or removal
| (ii) | If any of the tender rates other than a rate of levy payable by |  |  |  | such work people upon or in connection with the Works, and |  | (2) |  |  |  | of the object by a third party. Any such third party shall for the purposes of
|  | virtue of the Fiji National Training Act 1973, is increased or |  |  |  | what he would have paid had the alteration, cessation or new |  | Any notice required to be given by the preceding sub-clause shall be given |  |  |  | clause 18 of these Conditions be deemed to be a person for whom the
|  | decreased, or if a tender type ceases to be payable, of a new |  |  |  | type of contribution, levy or tax not become effective, shall, as |  | within a reasonable time after the occurrence of that to which the notice |  |  |  | Employer is responsible and not to be a sub-contractor.
|  | type of contribution, levy or tax which is payable by a person in |  |  |  | the case may be, paid to or allowed by the Contractor. |  | relates, and the giving of a written notice in that time shall be a condition |  |  |  | (3)
|  | his capacity as an employer becomes payable after the date of |  |  | (iii) | The prices contained in the Schedule of Rates are based upon |  | precedent to any payment being made to the Contractor in respect of the |  |  |  | If in the opinion of the Architect compliance with the provisions of sub-
|  | tender, then in any such case the net amount of the difference |  |  |  | the types and rates of refund of contributions, levies and taxes |  | event in question. |  |  |  | clause (1) of this Condition or with an instruction issued under sub-clause
|  | between what the Contractor actually pays or will pay in |  |  |  | payable by a person in his capacity as an employer and upon |  | (3) |  |  |  | (2) of this Condition has involved the Contractor in direct loss &/or expense
|  | respect of work people whilst they are engaged upon or in |  |  |  | the types and rates of premium receivable by a person in his |  | The Quantity Surveyor and the Contractor may agree what shall be deemed |  |  |  | for which he would not be reimbursed by a payment made under any other
|  | connection with the Works or because of his employment of |  |  |  | capacity as an employer being in each case types and rates |  | for all the purposes. of this Contract to be the net amount payable to or |  |  |  | provision in this Contract then the Architect shall either himself ascertain or
|  | such work people upon or in connection with the Works, & |  |  |  | which at the date of tender are receivable by the Contractor. |  | allowable by the Contractor in respect of the occurrence of any event such |  |  |  | shall instruct the Quantity Surveyor to ascertain the amount of such loss
|  | what he would have paid had the alteration, cessation or new |  |  |  | Such a type and such a rate are in the next sub-paragraph |  | as is referred to in any of the provisions listed in sub-clause (1) of this |  |  |  | and/ or expense. Any amount from time to time so ascertained shall be
|  | type of contribution, levy or tax not become affective, shall, as |  |  |  | referred to as a 'tender type' and a 'tender rate'. |  | Condition. |  |  |  | added to the Contract Sum, and if an Interim Certificate is issued after the
|  | the case may be, be paid to or allowed by the Contractor. |  |  | (iv) | If any of the tender rates is increased or decreased or if a |  | (4) |  |  |  | date of ascertainment any such amount shall be added to the amount which
| (iii) | The prices contained in the Schedule of Rates are based upon |  |  |  | tender type ceases to be payable or if a new type of refund of |  | Any amount which from time to time becomes payable to or allowable by |  |  |  | would otherwise be stated as due in such a Certificate.
|  | the types and rates of refund of contributions, levies and taxes |  |  |  | any contribution levy or tax payable by a person in his capacity |  | the Contractor by virtue of clause 31A or clause 31B or clause 31C of these
|  | payable by a person in his capacity as an employer & upon the |  |  |  | as an employer becomes receivable or if a new type of |  | Conditions shall, as the case may be, be added to or subtracted from: |  |  |  | 33 | Arbitration
|  | types and rates of premium receivable by a person in his |  |  |  | premium receivable by a person in his capacity as an employer |  | (a) | The Contract Sum; and |  |  | (1)
|  | capacity as an employer being in each case types and rates |  |  |  | becomes receivable after the date of tender, then in any such |  | (b) | Any amounts payable to the Contractor and which are calculated in |  |  | Provided always that in case any dispute or difference shall arise between
|  | which at the date of tender are receivable by the Contractor. |  |  |  | case the net' amount of the difference between what the |  |  | accordance with either sub-paragraph (i) or sub-paragraph (ii) of |  |  | the Employer or the Architect on his behalf and the Contractor, either during
|  | Such a type and such a rate are in the next sub-paragraph |  |  |  | Contractor actually receives or will receive in respect of work |  |  | paragraph (b) of sub-clause 2 of clause 26 of these Conditions; and |  |  | the progress or after the completion or abandonment of the Works, as to the
|  | referred to as a 'tender type' and a 'tender rate'. |  |  |  | people whilst they are engaged upon or in connection with the |  | (c) | The amount which would otherwise be stated as due in the next |  |  | construction of this Contract or as to any matter or thing of whatsoever
| (iv) | If any of the tender rates is increased or decreased or if a |  |  |  | Works or because of his employment of such work people |  |  | Interim Certificate. Provided: |  |  | nature arising thereunder or in connection therewith (including any matter or
|  | tender type ceases to be payable or if a new type of refund |  |  |  | upon or in connection with the Works, and what he would have |  |  | (i) | No addition to or subtraction from the amount which would |  | thing left by this Contract to the discretion of the Architect or the withholding
|  | of any contribution levy or tax payable by a person in his |  |  |  | received had the alteration, cessation or new type of refund or |  |  |  | otherwise be stated as due in an Interim Certificate shall be |  | by the Architect of any certificate to which the Contractor may claim to be
|  | capacity as an employer becomes receivable or if a new type |  |  |  | premium not become effective, shall, as the case may be, be |  |  |  | made by virtue of this sub-clause unless on or before the date |  | entitled or the measurement and valuation mentioned in clause 30(5)(a) of
|  | of premium receivable by a person in his capacity as an |  |  |  | allowed by or paid to the Contractor. |  |  |  | at which the total value of work, materials and goods is |  | these Conditions or the rights and liabilities of the parties under clauses 25
|  | employer becomes receivable after the date of tender, then in |  |  | (v) | The references in the two preceding sub-paragraphs to |  |  |  | ascertained for the purposes of that Certificate the Contractor |  | or 26 of these Conditions), then such dispute of difference shall be and is
|  | any such case the net amount of the difference between |  |  |  | premiums shall be consfrued as meaning all payments |  |  |  | shall have actually paid or received the sum which is payable |  | hereby referred to the arbitration and final decision of a person to be agreed
|  | what the Contractor actually receives or will receive in respect |  |  |  | howsoever they are described which are made under or by |  |  |  | by or to him in consequence of the event in respect of which |  | between the parties, or, failing agreement within 14 days after either party
|  | of work people whilst they are engaged upon or in connection |  |  |  | virtue of an Act of Parliament to a person in his capacity as an |  |  |  | the payment or allowance arises. |  | has given to the other a written request to concur in the appointment of an
|  | with the Works or because of his employment of such work |  |  |  | employer and which affect the cost to an employer of having |  |  | (ii) | No addition to or subtraction from the Contract Sum made by |  | Arbitrator, a person to be appointed on the request of either party by the
|  | people upon or in connection with the Works, and what he |  |  |  | persons in his employment. |  |  |  | virtue of this subclause shall alter in any way the amount of |  | President or a Vice-President for the time being of the Fiji Association of
|  | would have received had the alteration, cessation or new type |  |  | (vi) | The references in sub-paragraphs (i) to (iv) of this paragraph to |  |  |  | profit of the Contractor included in that Sum. |  | Architects.
|  | of refund or premium not become effective, shall, as the case |  |  |  | contributions, levies and taxes shall be construed as meaning |  | (5) |  |  |  | (2)
|  | may be, be allowed by or paid to the Contractor. |  |  |  | all impositions payable by a person in his capacity as an |  | Clause 31A, clause 31B and clause 31C shall not apply in respect of: |  |  |  | Such reference, except on article 3 or article 4 of the Articles of Agreement,
| (v) | The references in the two preceding sub-paragraphs to |  |  |  | employer howsoever they are described and whoever the |  | (a) | Work for which the contractor is allowed Daywork rates under clause |  |  | or on the questions whether or not the issue of an instruction is empowered
|  | premiums shall be construed as meaning all payments |  |  |  | recipient which are imposed under or by virtue of an Act of |  |  | 1l(4)(c) of these Conditions. |  |  | by these Conditions, whether or not a certificate has been improperly
|  | howsoever they are described which are made under or by |  |  |  | Parliament and which affect the cost to an employer of having |  | (b) | Work executed or materials or goods supplied by any nominated sub - |  |  | withheld or is not in accordance with these Conditions, shall not be opened
|  | virtue of an Act of Parliament to a person in his capacity as an |  |  |  | persons in his employment. |  |  | contractor or nominated supplier (fluctuations in relation to nominated |  |  | until after Practical Completion or alleged Practical Completion of the Works
|  | employer and which affect the cost to an employer of having |  | (b) | (i) | The prices contained in the Schedule of Rates are based upon |  |  | sub-contractors and nominated suppliers shall be dealt with under any |  |  | or termination or alleged termination of the Contractor's employment under
|  | persons in his employment. |  |  |  | the types and rates of duty if any and tax if any by whomsoever |  |  | provision in relation thereto which may be included in the appropriate |  |  | this Contract, or abandonment of the Works, unless with the written consent
| (vi) | The references in sub-paragraphs (i) to (iv) of this paragraph to |  |  |  | payable which at the date of tender are payable on the import, |  |  | sub-contract or contract of sale), or |  |  | of the Employer or the Architect on his behalf and the Contractor.
|  | contributions, levies and taxes shall be constructed as meaning |  |  |  | purchase, sale, appropriation, processing or use of the |  | (c) | Work executed by the Contractor for which a tender made under |  |  | (3)
|  | all impositions payable by a person in his capacity as an |  |  |  | materials and goods specified in the list attached thereto under |  |  | clause 27(g) of these Conditions has been accepted. |  |  | Subject to the provisions of clauses 2(2), 30(7) and 31D(3) of these
|  | employer howsoever they are described and whoever the |  |  |  | or by virtue of any Act of Parliament. A type and a rate so |  | (6) |  |  |  | Conditions, the Arbitrator shall, without prejudice to the generality of his
|  | recipient which are imposed under or by virtue of an Act or |  |  |  | payable are in the next sub-paragraph referred to as a 'tender |  | In Clause 31A and clause 31B of these Conditions: |  |  |  | powers, have power to direct such measurements and/or valuations as may
|  | Parliament and which affect the cost to an employer of having |  |  |  | type' and a 'tender rate', | [5 empty] | in his opinion be desirable in order to determine the rights of the parties and
|  | persons in his employment. |  |  | (ii) | If in relation to any materials or goods specified as aforesaid a |  | (a) | The expression 'the date of tender' means the date 10 days before the |  |  | to ascertain and award any sum which ought to have been the subject of or
(c) | (i) | The prices contained in the Schedule of Rates are based upon |  |  |  | tender rate is increased or decreased, or a tender type ceases |  |  | date fixed for the receipt of tenders by the Employer; and |  |  | included in any certificate and to open up, review and revise any certificate,
|  | the market prices of the materials and goods specified in the |  |  |  | to be payable or a new type of duty or tax becomes payable on |  | (b) | The expressions 'materials' and 'goods' include timber used in form- |  |  | opinion, decision, requirement or notice and to determine all matters in
|  | list attached thereto which were current at the date of tender. |  |  |  | the import, purchase, sale, appropriation, processing or use of |  |  | work but do not include other consumable stores, plant & machinery. |  |  | dispute which shall be submitted to him in the same manner as if no such
|  | Such prices are hereinafter referred to as 'basic prices', & the |  |  |  | those materials or goods, then in any such case the net |  | (c) | The expression 'work people' means persons whose rates of wages |  |  | certificate, opinion, decision, requirement or notice had been given.
|  | prices stated by the Contractor on the said list shall be deemed |  |  |  | amount of the difference between what the Contractor actually |  |  | and other emoluments and expenses are governed by the provisions |  |  | (4)
|  | to be the basic prices of the specified materials and goods. |  |  |  | pays in respect of those materials or goods, and what he would |  |  | of the Wages Regulation (Building and Civil & Electrical Engineering |  |  | The award of such Arbitrator shall be final and binding on the parties.
| (ii) | If after the date of tender the market price of any materials or |  |  |  | have paid in respect of them had the alteration, cessation or |  |  | Trades) Order, or by the provisions of some other wages regulation |  |  | (5)
|  | goods specified as aforesaid increases or decreases, then the |  |  |  | imposition not occurred, shall, as the case may be, be paid to |  |  | order for trades associated with the building industry, or by the terms |  |  | Whatever the nationality, residence or domicile of the Employer, the
|  | net amount of the difference between the basic price thereof & |  |  |  | or allowed by the Contractor. In this sub-paragraph the |  |  | of an agreement between the Contractor and a registered and |  |  | Contractor any subcontractor or supplier or the Arbitrator, and wherever the
|  | the market price payable by the Contractor and current when |  |  |  | expression 'a new type of duty or tax' includes an additional |  |  | recognised trade union. |  |  | Works, or any part thereof, are situated, the law of Fiji shall be the proper
|  | the materials or goods are bought shall, as the case may be, |  |  |  | duty or tax and a duty or tax imposed in regard to specified | [5 empty] | law of this Contract and in particular (but not so as Chapter 30) shall apply
|  | be paid to or allowed by the Contractor. |  |  |  | materials or goods in respect of which no duty or tax whatever |  | 31E |  |  |  | to any arbitration under this Contract wherever the same, or any part of it,
| (iii) | The references in the two preceding sub-paragraphs to 'market |  |  |  | was previously payable. |  | There shall be added to the amount paid to or allowed by the Contractor |  |  |  | shall be conducted. (14)
|  | prices' s hall be construed as including any duty or tax by | [5 empty] | under:
whomsoever payable which is payable under or by virtue of any
|  | Act of Parliament on the import, purchase, sale, appropriation, |  | 31C |  |  |  | (a) | Clause 31 A(a)(ii); (b) Clause 31 A(b)(ii); (c) Clause 31 A(b)(iv);
|  | processing or use of the materials or goods specified as |  | (1) |  |  |  | (d) | Clause 31 A(c)(ii); (d) Clause 31 B(a)(ii); (e) Clause 31 B(a)(iv);
|  | aforesaid. |  | If the Contractor shall decide subject to clause 17 of these Conditions to |  |  |  | (g) | Clause 31 B(b)(ii);
31B (13) |  |  |  | sublet any portion of the Works he shall incorporate in the sub-contract
The Contract Sum shall be deemed to have been calculated in the manner |  |  |  | provisions to the like effect as the provisions of clauses 31A, 30 and |  |  |  | 32 Antiquities
set out below and shall be subject to adjustment in the events specified |  |  |  | 31E/clauses 318, 310 and 31E (as applicable) which are applicable for the |  |  |  | (1)
hereunder: |  |  |  | purposes of this Contract. |  |  |  | All fossils, antiquities and other objects of interest or value which may be
(a) | (i) | The prices contained in the Schedule of Rates are based upon |  | (2) |  |  |  | found on the site or in excavating the same during the Works shall become
|  | the types and rates of contribution, levy and tax payable by a |  | If the price payable under such a sub-contract as aforesaid is decreased |  |  |  | the property of the Employer, and upon discovery of such an object the |  |  |  | (14) Where the parties do not wish the proper law of the contract to be the
|  | person in his capacity as an employer and which at the date of |  | below or increased above the price in such sub-contract by reason of the |  |  |  | Contractor shall forthwith: |  |  |  | law of Fiji and/or do not wish the provisions of the Arbitration Ordinance
|  | tender are payable by the Contractor. A type and a rate so |  | operation of the said incorporated provisions, then the net amount of such |  |  |  | (a) | use his best -endeavours not to disturb the object & shall cease work if |  |  | (Chapter 30) to apply to any arbitration under the contract held under the
|  | payable are in the next sub-paragraph referred to as a 'tender |  | decrease or increase shall, as the case may be, be allowed by or paid to the |  |  |  |  | and insofar as the continuance of work would endanger the object or |  |  | procedural law of another country appropriate amendments to this sub-
|  | type' and a 'tender rate'. |  | Contractor under this Contract. |  |  |  |  | prevent or impede its excavation or its removal; |  |  | clause should be made.
Copyright reserved in all drawings and the | [5 empty] | EMPLOYER | CONTRACTOR |  | PROJECT |  | SHEET TITLE |  |  | DESIGN | : SP | PROJECT NO. | 1
work executed from them. Figured dimensions | [8 empty] | test2 |  | FIJI STANDARD FORM OF
shall be read in preferance. Largest scaled | [10 empty] | BUILDING CONTRACT |  |  | PREP BY | admin | SHEET NO. | BC07
drawings shall take precedence. Check all |  |  | ARCHITECTS,DESIGN CONSULTANTS,PROJECT MANAGERS,INTERIOR DESIGNERS 26 MARA ROAD , P.O.BOX 16 , NAUSORI , FIJI ISLANDS PH.- 3400 287 , Email : designhut@connect.com.fj |  |  | WITNESS | WITNESS
dimensions on site. All discrepancies shall | [8 empty] | test |  | WITHOUT QUANTITIES |  |  | DATE | 02-09-2021 | REV:
be reported to the ARCHITECT ASAP | [8 empty] | test |  | PRIVATE EDITION 1978